## Title Sheet
Automate Onboarding Report
Prepared For: %CLIENTNAME%
Month, Year

## TOC & Schedule
Table of Contents
Audit Phase
Kick Off Call
Automate Server Review
| Templates Review | Cleanup query to make the automation easier to read.
Application Review
Plugins Review & Best Practice Plugins
| User Accounts Review | Section is good -> Add a tab that is more in depth on security options specifically how it's deployed
Patch Manager Review
Antivirus Review
ConnectWise Control Review
Audit Phase Review call
Audit Phase Action Items
Impact Phase
Ignite Review
Envrironment Review
PSA / Ticketing Review
Impact Phase Review Call
Impact Phase Action Items
Automation Phase
ProVal Best Practice Monitoring
Monitor Audit
Broken Monitor Audit
Offline Server Monitoring
Ignite Manager Configuration
Virtualization Manager Monitoring
Automation Phase Review Call
Automation Phase Action Items
Client Success Phase
Action Item Review
Schedule Training Call
Schedule Monthly Admin Call
Wrap Up Call & Project Completion
Notes
| Other notes | Onboarding/offboarding discussion? What needs to be installed on all machines? What needs to be removed from machines?
Security tab - Discuss further with Chris

## Audit Phase
Audit Phase Review
Back to TOC
In The Audit Phase of the onboarding ProVal will review the following items in your system:
Kickoff Call
MSP Information & Escalations
Automate Server Review
Server Hardware Review
Automate Agent on Server
Port Review
MySQL Version Review
Automate Patch Version
Database Backup Confirmation
my.ini Configuration Review
Large DB Table Review
Retention Settings
Templates Review
Automate Branding Review
Control Center Branding Review
Connection String / SSL Review
Access Modes Review
Title Bar Message Review
Application Review
Script Engine and Script Queue Review
Schedules Review
Failed Emails Review
Plugins Review
Plugin Review
Best Practice Plugins
Active Directory Plugin Review
Report Center Review
Ignite Manager Review
Virtualization Manager Review
User Accounts Review
LDAP Review
SSO Review
User Metrics
Review User Audit Levels
MFA/2FA Audit
User Password Settings
System Lockouts
Patch Manager Review
Patching Metrics
Agents Patching Review
Patch Approval and Denial
Stage Delay
Windows 10 Patching Review
Third Party Patching Review
Patch Manager Audit and Proposal
Antivirus Review | AV Metrics Summary
AV Plugin Review
AV Strategy Review
ConnectWise Control Review | Control Version Review
SSL Configuration
User Accounts
2FA/MFA Review
Extensions Review + Best Practice Extensions
Application Setting Review
Branding Review
Audit Phase Action Items
Consolidated List

## Kickoff Call
MSP Information & Escalations
Back to Audit Phase
MSP Information
Review Item | Information
Service Start date
Location
Time Zone
RMM Solution Hosted?
Hours + Overage
Approximate Endpoints
Approximate Employees
Peer Group Membership(s)
Compliance Clients | Are there any partners that non-US based resources should not be able to see in the environment?
Tools
Review Item | Information
Anti-Virus Solution(s)
Backup Solution(s)
PSA + FQDN
CW Automate Web Portal Address
CW Automate Server Name(s)
CW Control Web Portal Address
CW Control Server Name
Security Tools | Perch, Huntress, Threatlocker, etc.
ProVal ProSync Plugin Setup
Baseline Metrics Audit
Escalations
Review Item | Information
Business Hours Escalation
After Hours Escalation
Scheduled Maintenance Window
Emergency Maintenance Window

## Automate Server
Automate Server
Back to Audit Phase
Automate Server Hardware and Configuration
Automate Application Server |  |  |  | Hardware Review Action Items
Server Name | CPU / Cores | RAM / DB Review | Hard Disks | Task | Approved | Completed
Automate Database Server
Server Name | CPU / Cores | RAM / DB Review | Hard Disks
MySQL Version
Automate Version
Automate Agent Installed On Server?
Latest Successful Automate Backup
Non-VSS Third Party Backup Solution?
Automate Ports
Required Ports |  |  |  | Ports Review Action Items
Port(s) | Protocol | Status | Notes | Task | Approved | Completed
75 | UDP |  | Enhanced Heartbeat
443 | TCP |  | HTTPS (SSL) Communication
8484 | TCP |  | Solution Center Access
127.0.0.1 | N/A |  | Local Machine Access
Optional Ports
80 | TCP |  | Agent Communication
70 | TCP |  | Redirectors Without Tunnels
70-74 | UDP |  | Tunnels & Redirectors
8002 | TCP/UDP |  | Tunnels
40000-40050 | TCP |  | HTTP Connection View Web CC
40000-41000 | UDP |  | Tunnels & Redirectors
TLS Settings
TLS Version | Enabled |  |  | TLS Settings Action Items
1 | Yes |  |  | Task | Approved | Completed
1.1 | Yes
1.2 | Yes
1.3 | Yes
My.ini Configuration |  |  |  | My.ini Action Items
File Location |  |  |  | Task | Approved | Completed
Setting Name | Current Config | Suggested Config | Final Config
Innodb_buffer_pool_size
innodb_buffer_pool_Instances
Database Tables |  |  |  | DB Tables Action Items
Top 10 Largest Tables |  |  |  | Task | Approved | Completed
Table Name | Total Size
Retention Settings |  |  |  | Retention History Action Items
Setting | Value (days) |  |  | Task | Approved | Completed
Client Stats
Computer Stats
Location Stats
Active Commands
Failed Commands
Commands
Software
Hardware
Drives
Processes
Auditing
Scripts
Script logs
Critical Event Log Counts
Monitors
Event Log History
Probe Stats
Patching History
Back to Audit Phase
Note on A5: Best Practice: Four CPU cores or greater is recommended. RAM should be configured based on agent count (Up to 2,000 (8GB) and up to 5,000 (16GB). The server should have a split drive configuration, with the OS and database separated. Free space on drives should be greater than 15%.
Note on A9: Best Practice: Four CPU cores or greater is recommended. RAM should be configured based on agent count (Up to 2,000 (8GB) and up to 5,000 (16GB). The server should have a split drive configuration, with the OS and database separated. Free space on drives should be greater than 15%.
Note on A13: Best Practice: MySQL 5.6.39 is the minimum supported version for ConnectWise Automate. MySQL 5.7 is also supported by Automate as well and can be implemented with the right settings to the my.ini.
Note on A14: Best Practice: Keeping Automate fully patched is essential to have a stable system. It ensures bugs are fixed and provides new features.
Note on A15: Best Practice: The Automate agent should be installed on the Automate server. This allows script to be scheduled against the server to perform maintenance tasks.
Note on A16: Best Practice: The database backs up nightly, creating a zip file of the tables. The previous ten backups are kept and allow individual tables to be restored.
Note on A17: Best Practice: ProVal recommends taking a daily backup of Automate outside of the SQL backup performed by the tool. Please enter the tool in use as well as the frequency of that backup. ***Important Notice*** The backup product in use MUST be VSS aware or the third party backup will corrupt the CWA Database
Note on A19: Best Practice: Having all ports setup properly ensures that Automate will have the access it needs to perform properly. Please ask the client to confirm their firewall settings for the below ports.
Note on A34: Best Practice: Proper TLS settings help increase security for the Automate application and the agents when they check-in. Currently, CW recommends the TLS 1.2+ protocol for the Automate server and agents. Note: Endpoints/Agents using TLS 1.0 or 1.1 will not be able to check-in once the the protocols are closed down. Please verify that unsupported operating systems have their TLS versions adjusted before making any changes!
Note on A41: Best Practice: All database settings should be configured to the settings recommended by ConnectWise. This will ensure the best possible performance from the database and prevent issues from occurring that could crash the database.
Note on A47: Best Practice: Generally, tables should not over 1.5 GBs in size with the exception of the Eventlogs table. Tables over 1.5 Bgs in size should be reviewed to determine why the table is expanding to such a large size. Larger MSPs may have some exceptions for the size of tables.
Note on B62: Note: Active Commands history is in hours, not days.

## Template Review
Template Review
Back to Audit Phase
Default Template Review
Agent Branding |  |  |  | Agent Branding Action Items
Setting | Value |  |  | Task | Approved | Completed
Tray Text
Service Name
Show Tray Icon
Disable "Powered by Automate"
Custom Tray Icon
Control Center and Web Branding |  |  |  | Control Center Branding Action Items
Setting | Value |  |  | Task | Approved | Completed
Title
Control Center Custom Logo
Custom Splash Setting
Web Control Center Custom Logo
Web Control Center Custom Theme
SSL Configuration
Setting | Value |  |  | SSL Config Action Items
Connection String |  |  |  | Task | Approved | Completed
Using HTTPS?
IP Address as Backup
Access Modes |  |  |  | Access Modes Action Items
Setting | Enabled | Value |  | Task | Approved | Completed
Reboot Mode
Remote Access Mode
File Explorer Mode
Registry Editor Mode
Screenshot Mode
Schedules/Agent Upgrade Settings |  |  |  | Schedule or Agent Update Settings
Setting | Enabled | Start Time | Duration | Task | Approved | Completed
Agent Update Window
Note on A5: Best Practice: All branding should be configured, reducing confusion for clients and ensuring your company’s name is always at the forefront. Branding the Control Center provides a seamless look and is essential if end client IT departments have access. The Web Portal can also be customized and at minimum should have the company logo attached. Ideal size for the Control Center Splash logo is 435w x 255h pixels. The Control Center Logo - Min: 88 x 48 px ¦ Max: 192 x 48 px ¦ Max File Size: 64 Kb
Note on A13: Best Practice: The default template should handle the connection string for all machines as well as it should handle branding. It is possible to configure branding and the connection string on separate templates but it is not best practice and can complicate the system unnecessarily.
Note on A21: Best Practice: SSL is essential for ensuring clients have a secure connection to your Automate server. Configuring both your FQDN and IP address ensures clients can connect in the event of DNS issues.
Note on A27: Best Practice: The default template should handle all the system defaults for access modes. ProVal recommends Ask then Allow as the overall reboot mode. For Remote Access, File Explorer, Registry Editor, and Screenshot modes we recommend they are enabled and silent. Any exceptions can be handled with different templates applied via exception groups.
Note on A35: Best Practice: Agents should be able to update anytime they are online. ProVal recommends starting the window at 1 AM and allowing updates all day (23 hours)

## Application Review
Automate Application Setting Review
Back to Audit Phase
Application Review
Script Engine and Script Queue Review |  |  | Script Review Action Items
Review item | Value |  | Task | Approved | Completed
Script Backlog
Max Running Scripts
Scripts per Batch
Script Engine Review | [6 empty] | Script Engine Action Items
Script Name | MachineHours | LastRunTime | TotalRuns | LastRundate | Notes |  | Task | Approved | Completed
Machine Schedules |  |  |  | Schedules Action Items
Review item | Schedule Adjusted? | Schedule Approved? |  | Task | Approved | Completed
Desktop |  |  |  | Load in ProVal best practice Schedules
Laptop
Server
Failed Emails |  |  |  | Email Action Items
Review Item | Value |  |  | Task | Approved | Completed
Number of Failed Emails: | #
Automate Server Email: | address@domain.com
Mail Type
Is mail flowing?
Back to Audit Phase
Note on A5: Best Practice: The script engine drives automation in the application. The script engine should be busy, but not overburdened. If the script queue is too busy then scripts may take longer than expected to run, or may not run at the correct time. It is also important to ensure that the number of scripts running concurrently and the scripts per batch are the appropriate size for the environment. There is no goldren rule for this, but generally speaking the default works properly for most partners < 10K agents. If an MSP is seeing issues with the script engine, the values can be adjusted in small increments until the issue subsides. Max running scripts can be moved in increments of 25. Scripts per batch can be moved in increments of 5. The Default settings for these are: Max Running Scripts: 300 Scripts per batch: 15 The next tier up could be Max Running Scripts: 325 Scripts per batch: 20
Note on B12: Number Of Database Hours used when running this script.
Note on C12: How long the script ran last time it was run.
Note on D12: How many total times the script has been run in the environment. (This value is impacted by script retention history.)
Note on E12: The last time the script was run.
Note on F12: ProVal's Notes about the script
Note on A38: Best Practice: Desktop/Laptop/Server schedules show how often data is updated in the database throughout the day. It is best practice to ensure that schedules are not overlapping and that schedules update data frequently enough that data will be accurate for the internal monitors.
Note on A44: Best Practice: There should be no failed emails. If failed emails exist, they should be reviewed and determined if that email is no longer valid, or if the Automate server is having issues connecting to the mail server.

## Plugins Review
Plugins and Best Practice Plugins Review
Back to Audit Phase
Plugins Review
Automate Plugin Metrics
Review Item | Value
Solution Center reload completed?
Total Plugins Installed | #
Enabled Plugins | #
Disabled Plugins | #
Automate Plugins | [7 empty] | Plugin Review Action Items
Plugin Name | Version | Author | Release Date | Enabled | Official Plugin |  |  | Task | Approved | Completed
Update Plugins?
Best Practice Plugins Review
Active Directory Plugin
Installed and Enabled?
AD Plugin Review |  |  |  |  | AD Plugin Review Action Items
Client Name | Domain Name | Creds Used | Status |  | Task | Approved | Completed
Report Center Plugin |  |  |  |  | Report Center Review Action Items
Installed and Enabled? |  |  |  |  | Task | Approved | Completed
Review Item | Value
Concurrent Report Generation | 4
Query Timeout | 60
Administrator Email | test@test.com
Ignite Manager Plugin |  |  |  |  | Ignite Manager Review Action Items
Plugin Name | Installed | Enabled | Configured |  | Task | Approved | Completed
Ignite Manager
Core Services Management Pack
Database Management Pack
Messaging Management Pack
ProVal Exchange 2016/2019 Monitoring | No
Network Port Management Pack
Web/Proxy Management Pack
Virtualization Manager Plugin |  |  |  |  | Virtualization Manager Review Action Items
Installed and Enabled? |  |  |  |  | Task | Approved | Completed
Credentials for ESXi Hosts
Client | Location | Credential Used
Back to Audit Phase
Note on A5: Best Practice: Keeping plugins updated is essential to ensuring proper functionality. ConnectWise recommends using as few plugins as possible, as plugins can conflict with one another. Having a high number of enabled plugins also puts a load on the database, slowing down overall system performance. Old or now unsupported plugins can leave the database bloated and can be removed if there is no further value provided.
Note on A51: Best Practice: The Active Directory plugin should be enabled and configured. The plugin allows for basic management of user accounts as well as syncs domain user accounts, creating them as contacts in Automate.
Note on A63: Best Practice: The Report Center plugin should be enabled and configured. The plugin allows for running and scheduling reports. Custom reports can also be designed and implemented.
Note on A70: Best Practice: The Ignite Manager plugin should be enabled and configured. The plugin allows for role based monitoring of critical server infrastructure and includes automation for restarting services based on the role detected on the device. The individual management packs should be configured to only look at devices under service plans.
Note on A80: Best Practice: The Virtualization Manager should be installed and enabled. Credentials should be configured for all clients with ESXi hosts. Passwords should ideally be unique for each client.

## User Accounts Review
User Accounts Review
Back to Audit Phase
User Review
Default User Settings |  |  | Default User Settings Review Action Items
Review Item | Value |  | Task | Approved | Completed
LDAP Configured
SSO Configured
Account Lockouts Property Enabled
Users Can Save Password
Total Number of Users
Users without Audit Level Everything
User Accounts | [6 empty] | User Review Action Items
Username | UserClasses | Audit Level | Last Logon | 2FA Mode | Integrator | SSO | Task | Approved | Completed
Example | SuperAdmin | Everything | 2020-11-02 11:06 | Google Auth | Yes | Yes
LDAP Review
SSO Review
User Metrics
Review User Audit Levels
MFA/2FA Audit
User Password Settings
System Lockouts
Back to Audit Phase
Note on A4: Best Practice: There are several best practice user settings to consider. LDAP - This can be setup, however with many partners moving to Azure AD, this can be troublesome. If Azure AD is available, ProVal recommends setting up SSO with Azure linked. Single Sign On - As ConnectWise pushes more of Automate to the cloud we will see less and less authentication via the CWA Database. SSO is the best way to prep for the future of the product. Lockouts - Ensuring that account lockouts are happening on failed logins helps increase security. ProVal recommends enabling the account lockout feature if it's not already enabled. Save Password - Typically in the thick client users are allowed to "save" their password for their login. We discourage this as a safety concern. Even with mandatory Multifactor Authentication it is best practice to not allow users to store passwords. Audit Level - ProVal recommends that all users have the audit level of "Everything." Firstly this helps keep tabs on what changes are made in Automate and it makes it easier to keep an eye on the system. The other advantage is several actions are able to be undone, so keeping track of those items might help fix something done accidentally.
Note on A13: Best Practice: Stale user accounts should be removed. Appropriate user classes should be assigned based on the users’ role within the company. All users should be set to the audit level “Everything”. ProVal recommends that users should not be allowed to save their passwords in the control center login screen. Account lockouts should be enabled after 5 failed login attempts. LDAP or SSO can be enabled to help simply user management.

## Patch Review
Patch Manager Review
Back to Audit Phase
Patching Metrics |  |  |  |  | Patch Manager Review Action Items
Review Item | Value |  |  |  | Task | Approved | Completed
Total Missing Patches - Filtered
Total Missing Patches - Unfiltered
Total Missing - Servers
Total Missing - Workstations
Machines Without Patch Policy
Machines Excluded from Patching
Patches Not Set
Patches Set
Stage Delay
Testing | # Days
Pilot | # Days
Third Party Patch Solution
ProVal Approval and Denial
Window 10 Build Updates |  |  |  |  | Win 10 Build Updates Action Items
Win 10 Build | # of Machines | % of total | Support End |  | Task | Approved | Completed
1507 |  |  | 2017-05-09 |  | Implement monitor solution?
1511 |  |  | 2017-10-10 |  | Script Imported and setup?
1607 |  |  | 2018-04-10 |  | Custom Table Imported?
1703 |  |  | 2018-10-09
1709 |  |  | 2019-04-09
1803 |  |  | 2019-11-12
1809 |  |  | 2020-11-10
1903 |  |  | 2020-12-08
1909 |  |  | 2021-05-11
2004 |  |  | 2021-12-14
2009/20H2 |  |  | 2022-05-10
21H1 |  |  | 2022-12-13
21H2 |  |  | 2023-06-13
Windows 11 |  |  | 2023-10-10
Patch Manager Audit
GroupName | MachinesinGroup | UpdatePolicy | PolicyStyle | StartTime | Duration | RebootPolicy | ApprovalPolicies | Notes
Back to Audit Phase
Note on A3: Best Practice: Every agent should have a Microsoft Update Policy applied, even if that policy is to not patch the agent. Without a policy applied, Microsoft updates are not able to be controlled for that agent. All patches should be set in the environment to ensure the MSP knows what will happen with every patch.
Note on A5: This number is filtered to show the total number of missing patches for machines that have a patching policy in Automate.
Note on A6: This number is the total number of patches missing in Automate if every Windows machine has a patch policy.
Note on A7: Total number of missing patches for servers that have a patch policy.
Note on A8: Total number of missing patches for workstations that have a patch policy.
Note on A9: The number of machines that do not have any patching policy applied to them.
Note on A10: The number of machines that have a patch, but a configuration that means it is not managed by Automate.
Note on A11: The number of patches in Automate without a setting. These patches are not approved for install and will not push to machines.
Note on A12: The number of patches with a setting applied to them.
Note on A13: Optional: Stage delay can be setup to help test patches on a smaller subset of machines first before making them available to the larger machine base. ProVal recommends 1 week in test and 1 week in pilot, but these numbers can be adjusted based on end client requirements.
Note on A16: Best Practice: Third Party patching can be licensed and configured to ensure compete patching of systems. Security holes are not just limited to the underlying OS and exploits can be made successfully through unpatched software. ProVal can help support either ConnectWise third party patching or the Ninite Solution in conjunction with Ninite Pro licensing.
Note on A17: ProVal can perform approval and denial for Windows patches in Automate. Please ask for further details if you would like ProVal to take over this process.
Note on A20: Note: The data here is typically filtered for Windows 10 Machines that are in a patch policy and have been online within the last 30 days. To see all data, please review the dataview named "Windows - Windows 10 Version Metrics + Filters"
Note on A37: Best Practice – Installing patches: Workstations should patch daily with an afternoon window being best. If patching is done overnight, daytime patching should be enabled. When agents miss their window they are then patched the next time they are online. Servers should patch weekly. Best Practice – Rebooting machines that require a reboot: Workstations should use the Suppress and Reboot option. This allows workstations to reboot when most convenient for the user. Reboots can be set with a deadline to ensure compliance. ProVal recommends a pop-up reminder every 120 minutes, and a deadline/forced reboot after 72 hours, with a 15 minute deadline message. Servers should use the “During +30 minute” reboot policy or scheduled reboot windows for an appropriate reboot time. Host Servers should be patched on a different day than any other role based server but can follow the above best practice. Host servers should have "pausing" enabled on Host shutdown. Please notify the primary consultant if there are any exceptions or clarifications required for any clients.

## Patch Proposal
Patch Manager Review
Back to Audit Phase
Patch Manager Proposal
GroupName | UpdatePolicy | PolicyStyle | StartTime | Duration | RebootPolicy | ApprovalPolicies | Notes
Approvals - Default | Do Nothing | Not Managed | 12:00:00 AM | 1 | --Not Set-- | Approvals - Default
Approvals - Workstations | Do Nothing | Not Managed | 12:00:00 AM | 1 | --Not Set-- | Workstation Overrides
Approvals - Servers | Do Nothing | Not Managed | 12:00:00 AM | 1 | --Not Set-- | Server Overrides
Patch Install - Workstations | Workstations - Everyday 3-5am |  | 3:00 | 2 | Suppress Reboot
Custom Workstation only groups go here
Patch Install - Servers | Saturday 1a - 3a |  | 1:00 | 2 | Reboot During Window + 30
Patch Install - Servers - VM Host | Sunday 1a - 3a |  | 1:00 | 2 | Suppress Reboot (Servers creates Ticket)
Custom Server or Server + Workstation groups go here
Patch Install - Servers - VM Cluster | Do Nothing |  |  |  | Do NOT Reboot
Do NOT Patch (Agent EDF) | Disable Windows Update |  |  |  | Do NOT Reboot
Do NOT Reboot (Agent EDF) | --Not Set-- |  |  |  | Do NOT Reboot
Patching Not Enabled (Location EDFs) | Do Nothing |  |  |  | Do NOT Reboot
Microsoft Update Policies | Update Mode | Daytime | Restore Point | Baseline | WOL
Workstations - Everyday 3-5am | Managed Mode - UI Disabled | Yes | Yes | Yes | No
Servers - Saturday 1a - 3a | Managed Mode | No | Yes | Yes | No
VM Hosts - Sunday 1a - 3a | Managed Mode | No | Yes | Yes | No
Do Nothing | Do Nothing | No | No | No | No
Disable Windows Update | Disable Windows Update - UI Disabled | No | No | No | No
Reboot Policies | Reboot Behavior | Reboot Mode | Set Maintenance | Scripting | Notes
During Microsoft Update Window +30min | During Windows Update | Ask then Allow | Yes | None
Suppress Reboot | Suppress Reboot and Alert | N/A | N/A | N/A | (Prompt 4hrs, 2 days, 15 min warn)
Do NOT Reboot | Scheduled | Ask then Deny | N/A | N/A | Set Schedule for Feb 31st ONLY
Link to ITG document for Approval Policy Details
Back to Audit Phase
Note on A3: Best Practice: Every agent should have a Microsoft Update Policy applied, even if that policy is to not patch the agent. Without a policy applied, Microsoft updates are not able to be controlled for that agent. All patches should be set in the environment to ensure the MSP knows what will happen with every patch.

## Patch Approvals
categoryname (Will be custom depending on what is in your system) | Proval Default Action (Workstations) | Proval Default Action (Servers)
.NET 5.0 | Approve | Approve
.NET Core 2.1 | Approve | Approve
.NET Core 3.1 | Approve | Approve
Active Directory Rights Management Services Client 2.0 | Approve | Approve
Applications | Approve | Approve
ASP.NET Web Frameworks | Approve | Approve
Azure File Sync agent updates for Windows Server 2012 R2 | Approve | Approve
Azure File Sync agent updates for Windows Server 2016 | Approve | Approve
Azure File Sync agent updates for Windows Server 2019 | Approve | Approve
Bing Bar | Deny | Deny
Bing IME | Approve | Approve
CAPICOM | Approve | Approve
Critical Updates | Approve | Approve
Definition Updates | Approve | Approve
Drivers | Ignore | Ignore
Exchange Server 2007 | Approve | Approve
Exchange Server 2010 | Approve | Approve
Exchange Server 2013 | Approve | Approve
Exchange Server 2016 | Approve | Approve
Exchange Server 2019 | Approve | Approve
Feature Packs | Approve | Approve
Forefront TMG | Approve | Approve
Kernel Updates | Approve | Approve
Microsoft Azure Backup Server V3 - Data Protection Manager | Approve | Approve
Microsoft Azure Information Protection Client | Approve | Approve
Microsoft Azure Information Protection Unified Labeling Client | Approve | Approve
Microsoft Azure Site Recovery Provider | Approve | Approve
Microsoft Defender Antivirus | Approve | Approve
Microsoft Dynamics CRM 2013 | Approve | Approve
Microsoft Dynamics CRM 2015 | Approve | Approve
Microsoft Dynamics CRM 2016 | Approve | Approve
Microsoft Lync 2010 | Approve | Approve
Microsoft Lync Server 2010 | Approve | Approve
Microsoft Lync Server 2013 | Approve | Approve
Microsoft SQL Server 2012 | Approve | Approve
Microsoft SQL Server 2014 | Approve | Approve
Microsoft SQL Server 2016 | Approve | Approve
Microsoft SQL Server 2017 | Approve | Approve
Microsoft SQL Server 2019 | Approve | Approve
Microsoft Works 9 | Approve | Approve
Office 2002/XP | Approve | Approve
Office 2003 | Approve | Approve
Office 2007 | Approve | Approve
Office 2010 | Approve | Approve
Office 2013 | Approve | Approve
Office 2016 | Approve | Approve
Office 365 Client | Approve | Approve
Office Communications Server 2007 R2 | Approve | Approve
Office Communicator 2007 R2 | Approve | Approve
Report Viewer 2005 | Approve | Approve
Report Viewer 2008 | Approve | Approve
Security Updates | Approve | Approve
Service Packs | Approve | Approve
Silverlight | Approve | Approve
Skype for Business Server 2015 | Approve | Approve
System Center 2012 R2 - Operations Manager | Approve | Approve
System Center 2012 SP1 - Operation Manager | Approve | Approve
Tools | Approve | Approve
Update Rollups | Approve | Approve
Updates | Approve | Approve
Upgrades | Deny | Deny

## Antivirus Review
Antivirus Review
Back to Audit Phase
Antivirus Review |  | Antivirus Review Action Items
Review Item | Value | Task | Approved | Completed
Managed Solution
Plugin Installed
Plugin Configured
Machines with Managed Solution
Machines with Other Solution
Machines with no AV Solution
AV Solution Uninstall configured on offboarding
Adjust Defender Definition Priority
Antivirus Data
AV Detection Data
Count Machines | AV Name
Note on A3: Best Practice: If available, the vendors plugin should be installed and enabled. These plugins typically provide installation scripts or built-in functionality to easily and efficiently deploy the antivirus application.
Note on A15: Best Practice: If available, the vendors plugin should be installed and enabled. These plugins typically provide installation scripts or built-in functionality to easily and efficiently deploy the antivirus application.

## CW Control Review
ConnectWise Control Review
Back to Audit Phase
CWC Review |  |  |  | Control Review Action Items
Review Item | Value |  |  | Task | Approved | Completed
Control Patch Version
SSL Configuration
Idle Time Lockouts | # Seconds
Auto Update
Auto Consent | # Seconds
Technician Survey
Agents no Check-in Session Group Created
Agents Breakdown by Client/Location
Multi-Factor / Two Factor Authentication Users |  |  |  | Control MFA Review Action Items
Username | MFA Status |  |  | Task | Approved | Completed
Extensions Review | [5 empty] | Extensions Review Action Items
Extension Name | Installed | Configured | Up To Date | Completed |  | Task | Approved | Completed
Advanced Configuration Editor
ConnectWise Automate Integration
RMM+
ConnectWise Manage Integration
ConnectWise View Integration (License req)
Back to Audit Phase
Note on A3: Best Practices: CW Control Patch: Keeping Automate fully patched is essential to have a stable system. It ensures bugs are fixed and provides new features. SSL Config: Enabling SSL on the Control server ensures that connections to the Web Portal are encrypted and secure.
Note on A11: Best Practice: Create session group: GuestConnectedCount = 0 AND LastConnectedEventTime < $30DAYSAGO
Note on A12: Best Practice: Create or adjust a group with the following: Subgroup Expression: CustomProperty2 Note: If the CW contol environment has been adjusted to no longer use CustomProperty2 for locations this may need to be mapped to a different value. The CW Control plugin in Automate will also need to be configured to map locations to the proper custom property. If this has never been adjusted then no action items should be required.
Note on A14: Best Practice: All users that have access to CW Control should have MFA/2FA, including the Admin user. This helps prevent unauthorized access to the application and, by extension, end user machines.
Note on A28: Best Practice: The App.config & Web.config extensions should be installed, as they allow for customization of ConnectWise Control. Everything else is optional, but useful and ProVal recommends installing and using the above extensions
Note on A33: Optional
Note on A34: Optional - Requires special licensing

## Audit Phase Action Items
Audit Phase Action Items - Consolidated
Back to Audit Phase | Back to TOC
Action Items
Task | Approved | Completed | FromTable
P1_HardwareActions
P1_HardwareActions
P1_PortsActions
P1_Myiniactions
P1_Myiniactions
P1_dbtablesactions
P1_BrandingAction
P1_CCbrandingAcion
P1_SSLAction
P1_AccessModesAction
P1_ScriptReviewActions
P1_ScriptEngineActions
Load in ProVal best practice Schedules |  |  | P1_SchedulesAction
P1_EmailAction
P1_PluginReviewActions
P1_ADpluginAction
P1_ReportCenAction
P1_ReportCenAction
P1_IgniteManagerAction
P1_VirtManagerAction
P1_UserReviewAction
P1_DefaultUserAction
P1_PatchManReviewAction
Implement monitor solution? |  |  | P1_PatchWin10Action
Script Imported and setup? |  |  | P1_PatchWin10Action

## Impact Phase
Impact Phase Review
Back to TOC
In the Impact Phase of the onboarding, ProVal will review the following items in your system:
Ignite Review
Location Level Ignite Review
Default Extra Data Field Review
Environment Cleanup
Agents Not Checking In
Missing Drives Review
Missing Roles
Groups Review
PSA & Ticket Review
Ticket Volume Review
Ticket Noise Review
Tickets in Database
Manage Plugin: Comment Placement
Manage Plugin: Auto-Import Review
Manage Plugin: Service Boards Review
Manage Plugin: Asset Sync Review
Manage Plugin: Category Mapping Discussion
Impact Phase Action Items
Consolidated List

## Ignite Review
Ignite Review
Back to Impact Phase
Ignite Review |  |  |  | Ignite Review Action Items
Review Item | # Servers | # Workstations |  | Task | Approved | Completed
Agents Under MSP Contract
Agents Not Under MSP Contract
Default EDF Settings |  |  |  | Default EDF Action Items
Review Item | Setting |  |  | Task | Approved | Completed
Server Service Plan
Workstation Service Plan
Enable Onboarding
Server Patching
Workstation Patching
Ignite Settings by Location
Client | Location | Onboarding | Server Service Plan | Workstation Service Plan | Servers Covered | Workstations Covered | Server Patching | Workstation Patching | Admin Creds | Cache Drive
Back to Impact Phase
Note on A3: Best Practice: All locations should have a service plan setup for workstations and servers. The sites with unmanaged machines should be set to “none” for the service plan indicating purposefully unmanaged machines. Patching should be configured at the location level for easy management.
Note on A11: Best Practice: The Location Level Default Extra Data Fields should be setup with the system defaults for new clients/locations and the boxes should be changed to manage by exception.
Note on A19: Best Practice: All sites should be configured with a service plan, even if that service plan indicates that no services are applied. (NonContract service plan.) This helps verify which clients are managed or not managed based on their service plans. The below data indicates sites that may be out of compliance or may need additional configuration.

## Environment Cleanup
Environment Cleanup
Back to Impact Phase
Environment Review
Agents Not Checking In |  |  | Agents No Check Action Items
Review Item | Value |  | Task | Approved | Completed
# Agents Not Check-in in > 30 Days
Highest Number of Days Without Check-in
Out of Date Data |  |  | Out of Date Data Action Items
Review Item | Value |  | Task | Approved | Completed
Setup ProVal Maintenance Script |  |  | Setup ProVal Maintenance Script
Total Missing Drives
Total Not Currently Detected Roles
Groups Review
GroupID | GroupPath | GroupName | # Machines | Template Name | AutoJoinScript | AutoJoin Name | Internal | Remote | Total | Scripts | Master | Group Notes | Recommendation | ProVal Notes
Groups Review Action Items
Task | Approved | Completed
Back to Impact Phase
Note on A5: Best Practice: All outdated agents should be retired or have their connection issues resolved. Outdated agents bring down patching scores and use up Automate licenses.
Note on A10: Best Practice: Missing Drives Missing drives should be removed, otherwise false alerts can be generated and waste valuable technician time. The Remove Nonexistent Drives script can be scheduled to run against the Automate server to automate the removal process on a scheduled basis. Not Detected Roles Not currently detected roles should be removed, otherwise role based monitoring will generate false alerts. The Remove Not Detected Roles script can be scheduled to run against the Automate server to automate the removal process on a scheduled basis.
Note on A16: Best Practice: Groups are a great way to create functional or organizational units in Automate. However, groups can lose their purpose over time, or can be better serviced via internal monitor. We will review and discuss all non-standard groups in the environment and decide whether it is best to keep/delete/modify/replace groups in the environment to make things more efficient or easy to manage. Action items are below the table.

## PSA & Ticket Review
PSA & Ticket Review
Back to Impact Phase
PSA Review
Ticket Volume |  |  | Ticket Volume Action Items
Review Item | Value |  | Task | Approved | Complete
Total Tickets in DB
Average Ticket Volume Per Day
Average Ticket Volume Per Month
Average Ticket Volume Per Year
Average Tickets Per Machine Per Day
Average Tickets Per Machine Per Month
Ticket Noise |  |  | Ticket Noise Action Items
Monitor Name | Monitor Type | # Of Tickets Last 30 Days | Task | Approved | Complete
PSA Plugin Integration and Configuration
Default Service Boards |  |  | Default Service Board Action Items
Ticket Type | Service Board |  | Task | Approved | Complete
Control Center Tickets
Automate Tray Tickets
Monitor/Script/Email Tickets
Service Board Audit |  |  | Service Board Action Items
Review Item | Value |  | Task | Approved | Complete
Service Board Mapping | X of X
Service Board Name | Imported?
Manage <--> Automate Mappings |  |  | CWA / CWM Mapping Action Items
Review Item | Value |  | Task | Approved | Complete
Ticket Status Mapping | X of X
Ticket Priority Mapping | X of X
Total Category Mapping | X of X
Ticket Category Discussion |  |  | Ticket Category Action Items
Review Item | Value |  | Task | Approved | Complete
Use ProVal Mapping?
Granularity | Service Board / Priority / Service Type / Sub Type / Item
CW Manage Plugin Options |  |  | CWM Plugin Optional Action Items
Review Item | Value |  | Task | Approved | Complete
Auto Import
Auto Import For Import
Auto Import After Import
Ticket Comment Placement
Script Workflow User
Back to Impact Phase
Note on A5: Best Practice: While there is no magic number to the amount of tickets that should be received in a day, all tickets received should have a clear plan of action. If the process for a ticket is unknown, it may be noise and should be reviewed to determine if what generated it can be disabled. ProVal recommends deleting tickets older than 90 days to maintain database size and performance. Tickets will remain in ConnectWise Manage until they are deleted there.
Note on A10: Note: If the DB tickets are being cleared regularly, this number may not be accurate!
Note on A14: Best Practice: Tickets that alert excessively should be reviewed to determine if the alert is valid, has a clear plan of action, and if it can be automated. If a ticket does not require action, then it most likely doesn’t need to be generated.
Note on A28: Best Practice: All the default service boards should be set. Default service boards should only be used as a fallback, with ticket mapping directing tickets to the appropriate boards.
Note on A34: Best Practice: All service boards that Automate tickets will be synced with, or moved to, must be synced with the Manage plugin in Automate. If an Automate ticket is moved to a board that is not synced with the Automate plugin, the sync between Automate and Manage will be broken.
Note on A50: Best Practice: Map all statuses, all priorities, and all ticket categories to ensure tickets flow to the correct boards in the PSA. Unmapped statuses and priorities will cause ticket sync failures. All values should be mapped between Automate and the PSA. Unmapped tickets will be directed to the default boards configured.
Note on A56: Best Practice: The current ticket categorization mapping system tends to lead to confusion for the team. It's not always clear what ticket will end up where in the PSA. ProVal recommends creating new ticket categories that match the boards in the PSA. Normal ticket categories map like this: Disk Drive --> Service Desk ¦ P3 ¦ Proactive ¦ Drive ¦ Space ProVal Recommends creating the ticket category of ServiceDesk - P3 - Proactive - Drive - Space When this category is mapped in a monitor there is no confusion on what the ticket will do when it reaches the PSA.
Note on A62: Best Practice: NOTE: Auto Import is not currently functional as of 2021.12 for Automate or the CWM Plugin. The Auto Import options are optional, but it can help streamline the onboarding process. ProVal recommends that ticket comments from Automate go to the internal notes section of Manage tickets to minimize the chance of end customers seeing information the MSP may not want them to see. Script can be executed from workflows in Manage and ProVal recommends getting it enabled to help provide available automation to the team without having to leave Manage.

## Impact Phase Action Items
Impact Phase Action Items - Consolidated
Back to Impact Phase |  | Back to TOC
Action Items
Task | Approved | Completed | FromTable
P2_IgniteReviewAction
P2_IgniteReviewAction
P2_IgniteReviewAction
P2_DefaultEDFAction
P2_DefaultEDFAction
P2_DefaultEDFAction
P2_NoCheckinActions
P2_NoCheckinActions
P2_OutOfDateActions
P2_OutOfDateActions
P2_GroupReviewActions
P2_GroupReviewActions
P2_GroupReviewActions
P2_GroupReviewActions
P2_TicketVolAction
P2_TicketNoiseAction
P2_DefServiceBoardAction
P2_ServiceBoardAction
P2_MappingsAction
P2_TicketCatAction
Test | Yes |  | P2_CWMPluginOptionalAction

## Automation Phase
Automation Phase Review
Back to TOC
In the Automation Phase of the onboarding ProVal will review the following items in your system:
Monitoring Audit
ProVal Best Practice Monitoring
Monitor Audit
Broken Monitor Audit
Offline Server Monitoring
Ignite Manager Configuration
Virtualization Manager Monitoring
Network Device Review
Probe Review
Network Device Monitoring
Automation Phase Action items
Consolidated List

## Best Practice Monitoring
ProVal Best Practice Monitors
Back to Automation Phase
Best Practice Monitors
Monitor Name | Alert Template | Monitor Type | Applies to | Ticket Category | Approved | Completed? | Notes
Hyper-V - Aging Snapshot | Default - Create Automate Ticket | Remote | Server |  |  |  | Hyper V Server Role Group Only
Hyper-V - Replication Status | Default - Create Automate Ticket | Remote | Server |  |  |  | Hyper V Server Role Group Only
ProVal - Production - Agent - No Checkin for More Than 30 Days* | ~RMM+ Autofix With Reinstall
ProVal - Production - Active Directory - Domain Admin Recently Created | Default - Create Automate Ticket | Internal | Server+Workstation |  |  |  | Requires the Active Directory Plugin
ProVal - Production - Active Directory - Enabled Test Accounts | Default - Create Automate Ticket | Internal | Global |  |  |  | Requires the Active Directory Plugin
ProVal - Production - Active Directory - Sync Out of Date | ~Autofix - RMM+ AD Sync Out of Date | Internal | Global |  |  |  | Requires the Active Directory Plugin
ProVal - Production - Agent - CW Control Needs Repair | ~Autofix - CWControl Repair | Internal | Global
ProVal - Production - Agent - Dell Hardware Monitoring | ~CUSTOM - Ticket Creation - Computer | Internal | Server |  |  |  | Requires Dell OpenManage to be installed
ProVal - Production - Agent - Drive Errors and Raid Failures | Default - Create Automate Ticket | Internal | Server+Workstation
ProVal - Production - Agent - Crystal Disk Info Audit | ~CUSTOM - Ticket Creation - Computer | Internal | Server+Workstation
ProVal - Production - Agent - Drive Space Check | ~Autofix - ProVal Drive Space Cleanup | Internal | Server
ProVal - Production - Agent - HP Hardware Monitoring | ~CUSTOM - Ticket Creation - Computer | Internal | Server |  |  |  | Require HP Insight Manager to be installed
ProVal - Production - Agent - Offline Server | ~Autofix - RMM+ Server Offline | Internal | Server
ProVal - Production - Agent - Shutdown Unexpected | Default - Create Automate Ticket | Internal | Server
ProVal - Production - Automate - Machines With Stuck Commands | ~Autofix - Clear Stuck Commands | Internal | Global
ProVal - Production - Patching - Machines Missing X+ Patches | Default - Create Automate Ticket | Internal | Server+Workstation
ProVal - Production - Patching - Windows 10 Build Upgrades [G] | ~Autofix - Upgrade Windows 10 Build | Internal | Global
ProVal - Production - Security - Possible Brute Force Attack [G] | Default - Create Automate Ticket | Internal | Server+Workstation
ProVal - Production - Software - Missing Vendor Admin Software | Default - Create Automate Ticket | Internal | Server
ProVal - Production - Windows - Fast Boot Enabled [Role] | ~Autofix - Disable Fastboot | Internal | Server+Workstation
ProVal - Production - Patching - Empty Patch Window | ~Empty Patch Window Autofix
ProVal Server Monitoring Solution Set
*Remote Drive Space Monitor Creation - Servers | Default - Create Automate Ticket | Remote | Server |  |  |  | Discuss threshold! These are generated via script and are not handled at the group level
*Remote Drive Space Monitor Creation - Workstations | ~Autofix - ProVal Drive Space Cleanup | Remote | Workstation |  |  |  | Discuss threshold! These are generated via script and are not handled at the group level
ProVal - Production - Security - Stale Bitlocker Data [G]
Automate Server Monitoring
Monitor Name | Alert Template | Monitor Type | Applies to | Ticket Category | Approved | Completed? | Notes
ProVal - Production - Automate - Ticket Sync Unsuccessful | ~Autofix - Email Unsycned Ticket Info | Internal | Global |  |  |  | Email:
Monitor Disabled Script | Default - Create Automate Ticket | Internal | Global
ProVal - Production - Automate - Less Than X Licenses Remaining [G] | Default - Create Automate Ticket | Internal | Global
Optional Monitoring
Monitor Name | Alert Template | Monitor Type | Applies to | Ticket Category | Approved | Completed? | Notes
ProVal - Production - Active Directory - Account Disabled [G] | Default - Create Automate Ticket | Internal | Global |  |  |  | Requires the Active Directory Plugin
ProVal - Production - Active Directory - GPO Modified | Default - Create Automate Ticket | Internal | Global
SSL Cert Monitor | Default - Create Automate Ticket | Remote | Server |  |  |  | IIS Server Role Group Only
Windows License Monitor | Default - Create Automate Ticket | Remote | Server+Workstation
ProVal - Production - Active Directory - Password Expires This Week [G] | ~Autofix - Notify User of Password Expiration | Internal | Global |  |  |  | Requires the Active Directory Plugin
ProVal - Production - Agent - Duplicate Serial Number
ProVal - Production- Unresponsive Huntress Agents
ProVal - Production - AV - Disabled
ProVal - Production - AV - Out of Date
Vulnerability Monitoring
Monitor Name | Alert Template | Monitor Type | Applies to | Ticket Category | Approved | Completed? | Notes
CVE monitors?
Back to Automation Phase
Note on A3: This is the best practice list of monitors that ProVal recommends. Most monitors, if not all, should be used by MSPs to watch their devices and their Automate application. ProVal has a lot more available content than what is available on this list. Please ask your consultant for a full list of all available content or refer to the ProSync plugin.
Note on B13: Chase Murphy: Double check the script works
Note on A42: Discuss GPO auditing solution and monitoring
Note on B45: Options: Run autofix that emails the user directly, please supply desired language in the script. This can just generate a ticket into manage and then setup a workflow that has the matching contact to notify them from Manage.

## Monitor Audit
Monitor Audit | Legend
Back to Automation Phase | Good | Replace
Monitor Audit | Disable | Question
Note on D2: This is a monitor we would like to keep in production.
Note on E2: These are monitors ProVal would like to replace with custom versions.
Note on A3: This list will display every group based or global monitor in the environment and any pertinent information about the monitors. Please review all monitors and decide on which monitors to keep, which monitors to replace, and which monitors to remove.
Note on D3: This is a monitor we would want to remove from production or possibly even remove from the environment
Note on E3: These are monitors that we were not sure what the original purpose might have been. We would like to discuss this monitor and see what we can do to improve it.

## Broken Monitors
Broken Monitors
Back to Automation Phase
Broken Monitors Review |  |  |  | Broken Monitors Action Items
Monitor Name | DataOut | Group Notes | Group Applied | Task | Approved | Complete
Back to Automation Phase
Note on A3: Sometimes monitors to not write the correct values back into the database which can cause alerts to be missed. This is not something that happens very often, but it does happen from time to time. ProVal will review any of these monitors with potential issues and get the repaired. This is an item we will review monthly as part of keeping the system healthy.

## Offline Server Monitoring
Offline Server Monitoring
Back to Automation Phase
Offline Server Audit |  | Offline Server Action Items
Audit Item | Value | Task | Approved | Completed
Heartbeat Enabled?
Number of current Offline Server monitors
Description of current offline server monitoring
Example: LT - Offline Servers, Applied to 24x7 group, Running ~Autofix Server Offline Script, The alert template sends and email to email@email.com as well as a P1 ticket to the helpdesk board. The monitor will trigger if an agent has not checked in within the last 6 minutes and if the heartbeat has not contacted in 30 seconds. The monitor checks every 5 minutes.
Back to Automation Phase
Note on A3: Best Practice: As one of the most critical monitors in Automate, it is imperative that this monitor is functioning properly. The default LT – Offline Servers monitor works, however it does not account for some heartbeat scenarios that may cause the monitor to not trigger properly. ProVal recommends installing out best practice version of this monitor that handles for broken heartbeat scenarios. Ideally, the monitor should be configured with the ~Autofix Action Server Offline Script alert template which then calls the Server Offline alert template. This configuration runs the script to perform basic troubleshooting, which is appended to the ticket. ProVal also finds that the default thresholds lead to some false positives. We encourage partners to adjust the timing from the standard 6 minute no check-in and 30 second no heartbeat to between 8-12 minutes for last contact and 2-4 minutes no heartbeat.
Note on A8: Please indicate the following items in the description. 1. Monitor Name 2. Group applied 3. Alert Template 4. Description of alert template (Include ticket category + mapping) 5. Last contact threshold 6. Last heartbeat threshold 7. Check interval Please add as many rows as necessary for multiple monitors. Also indicate if there are any other groups where the monitor is applied and what actions it may be taking.

## Ignite Manager Monitoring
Ignite Manager Monitoring
Back to Automation Phase
Ignite Manager Plugins
Management Pack Action Items
Review Item | Installed | Enabled | Up To Date | Initial Setup Complete | Use MSP Contracts | Task | Approved | Completed
Core Services Management Pack | Yes | Yes | Yes
Database Management Pack | Yes | Yes | Yes
Ignite Manager | Yes | Yes | Yes
Messaging Management Pack plugin | Yes | Yes | Yes
Network Port Management Pack | Yes | Yes | Yes
Web/Proxy Management Pack plugin | Yes | Yes | Yes
Ignite Manager Monitors | [5 empty] | Ignite Manager Monitoring Action Items
Management Pack | Monitor | Alert Template | Ticket Category | Data Collection | Applies to Role | Task | Approved | Completed
Back to Automation Phase
Note on A3: Best Practice: All Ignite Manager management packs should be updated, installed, and enabled. These management packs provide current monitoring for all types of servers and applications. Our standard monitoring setup only alerts on critical services/events and does not alert on most performance metrics. Please review the list of monitors below by server role and our best practice for each management pack.

## Virt Manager Monitoring
Virtualization Manager Monitoring
Back to Automation Phase
Virtualization Manager Monitors
Virtualization Manager Monitor Action Items
Monitor | Enabled | Operator | Value | Interval | Alert Template | Task | Approved | Completed
Back to Automation Phase
Note on A3: Best Practice: As mentioned earlier during the onboarding, the Virtualization Manager can help manage and monitor your ESXi and Hyper-V hosts as well as their guests/virtual machines. Part of this implementation is going through available monitors and the ProVal best practice monitors. ProVal has custom alerting for the Virtualization Manager that makes the tickets significantly more useful than the stock monitors.
Note on E5: In minutes

## Probe Review
Network Device Monitoring
Back to Automation Phase
Probe Review
Network Probe Action Items
Client | Location | Probe Status | Possible Probe | Probe Version | Notes | Task | Approved | Complete
Back to Automation Phase
Note on A3: Best Practice: The probe may not be the perfect solution for network monitoring but it is at least a good jumping off point for basic monitoring and gathering some SNMP information. The probe can be used to do things like backup device configurations, provide up/down monitoring for network devices, deploy agents, and other various tasks. ProVal suggests having a probe at each site, ideally on a machine that is online 24x7 and that has good access to the end client network. A Domain Controller is a good choice for the network probe. All network probes should be running that latest version of the probe and we suggest ensuring all probes are running V2.

## Network Device Monitoring
Network Device Monitoring
Back to Automation Phase
Network Device Monitoring
Network Device Monitoring Action Items
Client | Location | Network Device | Set to Alert | Alert Template | Notes | Task | Approved | Completed
Back to Automation Phase
Note on A3: Best Practice: The Network device management screen allows users to setup basic online/offline monitoring for network devices. Below is an audit for any devices with this setup or not setup. The probe is not the most reliable method for this when there are other great tools like Auvik, PRTG, or Logic Monitor. But the probe can get the ball rolling on monitoring for the network devices at a base level.

## Automation Phase Action Items
Automation Phase Action Items - Consolidated
Back to Automation Phase |  | Back to TOC
Action Items
Task | Approved | Completed | FromTable
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_OfflineServerAction
W3_IgniteManPluginAction
W3_IgniteManPluginAction
W3_IgniteManMonitorsAction
W3_IgniteManMonitorsAction
W3_VirtManMonAction
W3_NetProbeAction
W3_NetProbeAction
W3_NetProbeAction
W3_NetDeviceMonAction
W3_NetDeviceMonAction

## Client Success Phase
Client Success Phase Review
Back to TOC
In the Client Success Phase of the onboarding ProVal will work on wrapping up the project!
Action Items
Consolidated Action Item Review
Schedule Meetings
Training Call
Monthly Admin Call
Wrap up Call & Project Completion
Approval
Notes

## Consolidated Action Items
Consolidated Action Items
Back to Client Success Phase |  | Back to TOC
Action Items
Task | Approved | Completed | FromTable
P1_HardwareActions
P1_HardwareActions
P1_PortsActions
P1_Myiniactions
P1_Myiniactions
P1_dbtablesactions
P1_BrandingAction
P1_CCbrandingAcion
P1_SSLAction
P1_AccessModesAction
P1_ScriptReviewActions
P1_ScriptEngineActions
Load in ProVal best practice Schedules |  |  | P1_SchedulesAction
P1_EmailAction
P1_PluginReviewActions
P1_ADpluginAction
P1_ReportCenAction
P1_ReportCenAction
P1_IgniteManagerAction
P1_VirtManagerAction
P1_UserReviewAction
P1_DefaultUserAction
P1_PatchManReviewAction
Implement monitor solution? |  |  | P1_PatchWin10Action
Script Imported and setup? |  |  | P1_PatchWin10Action
P1_AVAction
P1_CWCAction
P1_CWCMFAAction
P1_CWAExtensionAction
P2_IgniteReviewAction
P2_IgniteReviewAction
P2_IgniteReviewAction
P2_DefaultEDFAction
P2_DefaultEDFAction
P2_DefaultEDFAction
P2_NoCheckinActions
P2_NoCheckinActions
P2_OutOfDateActions
P2_OutOfDateActions
P2_GroupReviewActions
P2_GroupReviewActions
P2_GroupReviewActions
P2_GroupReviewActions
P2_TicketVolAction
P2_TicketNoiseAction
P2_DefServiceBoardAction
P2_ServiceBoardAction
P2_MappingsAction
P2_TicketCatAction
P2_CWMPluginOptionalAction
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_OfflineServerAction
P3_IgniteManPluginAction
P3_IgniteManPluginAction
P3_IgniteManMonitorsAction
P3_IgniteManMonitorsAction
P3_VirtManMonAction
P3_NetProbeAction
P3_NetProbeAction
P3_NetProbeAction
P3_NetDeviceMonAction
P3_NetDeviceMonAction

## Schedule Meetings
Schedule Meetings
Back to Client Success Phase
Call Schedules
Task | Date Scheduled | Time Scheduled | Approved | Complete
Team training
Monthly Call
Back to Client Success Phase
Note on A3: Training: ProVal provides a training for level 1-3 help desk team members aimed at teaching the team how to use Automate more effectively. The main mission of this training is to help the team understand all of the functions of the RMM so they can work without interrupting end users. This training should better enable them to support from the backend using Automate. This training will be recorded and shared back to the MSP. Monthly Call: During this call, ProVal will sit down with the MSP for about an hour and discuss the state of the environment, any issues or overarching goals the MSP is trying to accomplish, as well as any new content developed by ProVal that may help the MSP. This is the ideal forum to bring up any new development items the MSP may be interested in pursuing.

## Wrap Up Call-Project Completion
Project Completion
Back to Client Success Phase |  | Back to TOC
Wrap up call
Task | Approved | Completed | Date | Consultant Initials
Wrap up Call
Project Complete
Notes
Task | Approved | Completed
Back to Client Success Phase
Note on A3: Completing the project: Please ensure that all action items are completed, or that any remaining items are converted to tickets. Please receive a verbal confirmation that the MSP feels the project is complete and then close out the project.
Note on A10: Notes: Please write up any items that didn't fit into the original SOW or that we are covering outside of the standard SOW for the MSP.

## Data Sources
Patching Validation | Reboot Validation | Reboot Mode
Do Nothing | Suppress Reboot and Alert | Not Set
Enable Windows Update Default | During Windows Update | Now
Disable Windows Update | Scheduled | Ask
Disable Windows Update - UI Disabled | Disable Reboot Window - Follow Mode Setting | Ask then Allow
Managed Mode |  | Ask then Deny
Managed Mode - UI Disabled |  | N/A