## Title Sheet
Automate PEC
Prepared For: %CLIENTNAME%
Month, Year

## TOC & Schedule
Table of Contents
Audit Phase
Kick Off Call
Automate Server Review
Templates Review
Application Review
Plugins Review & Best Practice Plugins
User Accounts Review
Patch Manager Review
Antivirus Review
ConnectWise Control Review
Audit Phase Review call
Audit Phase Action Items
Impact Phase
Ignite Review
Envrironment Review
PSA / Ticketing Review
Impact Phase Review Call
Impact Phase Action Items
Automation Phase
ProVal Best Practice Monitoring
Monitor Audit
Broken Monitor Audit
Offline Server Monitoring
Ignite Manager Configuration
Virtualization Manager Monitoring
Automation Phase Review Call
Automation Phase Action Items
Client Success Phase
Action Item Review
Schedule Training Call
Schedule Monthly Admin Call
Wrap Up Call & Project Completion
Notes

## Audit Phase
Audit Phase Review
Back to TOC
In The Audit Phase of the onboarding ProVal will review the following items in your system:
Kickoff Call
MSP Information & Escalations
Automate Server Review
Server Hardware Review
Automate Agent on Server
Port Review
MySQL Version Review
Automate Patch Version
Database Backup Confirmation
my.ini Configuration Review
Large DB Table Review
Retention Settings
Templates Review
Automate Branding Review
Control Center Branding Review
Connection String / SSL Review
Access Modes Review
Title Bar Message Review
Application Review
Script Engine and Script Queue Review
Schedules Review
Failed Emails Review
Plugins Review
Plugin Review
Best Practice Plugins
Active Directory Plugin Review
Report Center Review
Ignite Manager Review
Virtualization Manager Review
User Accounts Review
LDAP Review
SSO Review
User Metrics
Review User Audit Levels
MFA/2FA Audit
User Password Settings
System Lockouts
Patch Manager Review
Patching Metrics
Agents Patching Review
Patch Approval and Denial
Stage Delay
Windows 10 Patching Review
Third Party Patching Review
Patch Manager Audit and Proposal
Antivirus Review | AV Metrics Summary
AV Plugin Review
AV Strategy Review
ConnectWise Control Review | Control Version Review
SSL Configuration
User Accounts
2FA/MFA Review
Extensions Review + Best Practice Extensions
Application Setting Review
Branding Review
Audit Phase Action Items
Consolidated List

## Automate Server
Automate Server
Back to Audit Phase
Automate Server Hardware and Configuration
Automate Application Server |  |  |  | Hardware Review Action Items
Server Name | CPU / Cores | RAM / DB Review | Hard Disks | Task | Approved | Completed
Automate Database Server
Server Name | CPU / Cores | RAM / DB Review | Hard Disks
Server OS
Automate Backup Status
MySQL Version
Agent Count
TLS Settings
TLS Version | Enabled |  |  | TLS Settings Action Items
1 |  |  |  | Task | Approved | Completed
1.1
1.2
1.3
Retention Settings |  |  |  | Retention History Action Items
Setting | Value (days) |  |  | Task | Approved | Completed
Client Stats
Computer Stats
Location Stats
Active Commands
Failed Commands
Commands
Software
Hardware
Drives
Processes
Auditing
Scripts
Script logs
Critical Event Log Counts
Monitors
Event Log History
Probe Stats
Patching History
Back to Audit Phase
Note on A5: Best Practice: Four CPU cores or greater is recommended. RAM should be configured based on agent count (Up to 2,000 (8GB) and up to 5,000 (16GB). The server should have a split drive configuration, with the OS and database separated. Free space on drives should be greater than 15%.
Note on A9: Best Practice: Four CPU cores or greater is recommended. RAM should be configured based on agent count (Up to 2,000 (8GB) and up to 5,000 (16GB). The server should have a split drive configuration, with the OS and database separated. Free space on drives should be greater than 15%.
Note on A14: Best Practice: The database backs up nightly, creating a zip file of the tables. The previous ten backups are kept and allow individual tables to be restored.
Note on A15: Best Practice: MySQL 5.6.39 is the minimum supported version for ConnectWise Automate. MySQL 5.7 is also supported by Automate as well and can be implemented with the right settings to the my.ini.
Note on A18: Best Practice: Proper TLS settings help increase security for the Automate application and the agents when they check-in. Currently, CW recommends the TLS 1.2+ protocol for the Automate server and agents. Note: Endpoints/Agents using TLS 1.0 or 1.1 will not be able to check-in once the the protocols are closed down. Please verify that unsupported operating systems have their TLS versions adjusted before making any changes!
Note on B26: Note: Active Commands history is in hours, not days.

## Template Review
Template Review
Back to Audit Phase
Default Template Review
Agent Branding - Server |  |  |  | Agent Branding - Server Action Items
Setting | Value |  |  | Task | Approved | Completed
Tray Text
Service Name
Show Tray Icon
Disable "Powered by Automate"
Custom Tray Icon
Agent Branding - Workstation |  |  |  | Agent Branding - Workstation Action Items
Setting | Value |  |  | Task | Approved | Completed
Tray Text
Service Name
Show Tray Icon
Disable "Powered by Automate"
Custom Tray Icon
Agent Configuration
Setting | Value |  |  | Agent Config Action Items
Connection String |  |  |  | Task | Approved | Completed
Using HTTPS?
IP Address as Backup
Setting | Enabled | Start Time | Duration
Agent Update Window
Note on A5: Best Practice: All branding should be configured, reducing confusion for clients and ensuring your company’s name is always at the forefront. Branding the Control Center provides a seamless look and is essential if end client IT departments have access. The Web Portal can also be customized and at minimum should have the company logo attached. Ideal size for the Control Center Splash logo is 435w x 255h pixels. The Control Center Logo - Min: 88 x 48 px ¦ Max: 192 x 48 px ¦ Max File Size: 64 Kb
Note on A13: Best Practice: All branding should be configured, reducing confusion for clients and ensuring your company’s name is always at the forefront. Branding the Control Center provides a seamless look and is essential if end client IT departments have access. The Web Portal can also be customized and at minimum should have the company logo attached. Ideal size for the Control Center Splash logo is 435w x 255h pixels. The Control Center Logo - Min: 88 x 48 px ¦ Max: 192 x 48 px ¦ Max File Size: 64 Kb
Note on A21: Best Practice: SSL is essential for ensuring clients have a secure connection to your Automate server. Configuring both your FQDN and IP address ensures clients can connect in the event of DNS issues.
Note on A26: Best Practice: Agents should be able to update anytime they are online. ProVal recommends starting the window at 1 AM and allowing updates all day (23 hours)

## Application Review
Automate Application Setting Review
Back to Audit Phase
Application Review
Script Engine and Script Queue Review |  |  | Script Review Action Items
Review item | Value |  | Task | Approved | Completed
Max Running Scripts | 300
Scripts per Batch | 15
Machine Schedules |  |  |  | Schedules Action Items
Review item | Schedule Adjusted? | Schedule Approved? |  | Task | Approved | Completed
Desktop
Laptop
Server
Back to Audit Phase
Note on A5: Best Practice: The script engine drives automation in the application. The script engine should be busy, but not overburdened. If the script queue is too busy then scripts may take longer than expected to run, or may not run at the correct time. It is also important to ensure that the number of scripts running concurrently and the scripts per batch are the appropriate size for the environment. There is no goldren rule for this, but generally speaking the default works properly for most partners < 10K agents. If an MSP is seeing issues with the script engine, the values can be adjusted in small increments until the issue subsides. Max running scripts can be moved in increments of 25. Scripts per batch can be moved in increments of 5. The Default settings for these are: Max Running Scripts: 300 Scripts per batch: 15 The next tier up could be Max Running Scripts: 325 Scripts per batch: 20
Note on A10: Best Practice: Desktop/Laptop/Server schedules show how often data is updated in the database throughout the day. It is best practice to ensure that schedules are not overlapping and that schedules update data frequently enough that data will be accurate for the internal monitors.

## Plugins Review
Plugins and Best Practice Plugins Review
Back to Audit Phase
Plugins Review
Automate Plugins | [7 empty] | Plugin Review Action Items
Plugin Name | Version | Author | Release Date | Enabled | Official Plugin |  |  | Task | Approved | Completed
Review plugins that are not enabled.
Review unofficial plugins released before 2015.
Review deprecated / known issue plugins.
Best Practice Plugins Review
Active Directory Plugin
Installed and Enabled?
AD Plugin Review |  |  |  |  | AD Plugin Review Action Items
Client Name | Domain Name | Creds Used | Status |  | Task | Approved | Completed
Review Missing, Pending and Failed credentials.
Ignite Manager Plugin |  |  |  |  | Ignite Manager Review Action Items
Plugin Name | Installed | Enabled | Configured |  | Task | Approved | Completed
Ignite Manager
Core Services Management Pack
Database Management Pack
Messaging Management Pack
ProVal Exchange 2016/2019 Monitoring
Network Port Management Pack
Web/Proxy Management Pack
Ignite Updates Available?
Virtualization Manager Plugin |  |  |  |  | Virtualization Manager Review Action Items
Hyper-V Installed and Enabled? |  |  |  |  | Task | Approved | Completed
VMWare Installed and Enabled?
Locations Missing Credentials
Client | Location | # of VMs
ProVal
ProVal
Back to Audit Phase
Note on A44: Best Practice: The Active Directory plugin should be enabled and configured. The plugin allows for basic management of user accounts as well as syncs domain user accounts, creating them as contacts in Automate.
Note on A56: Best Practice: The Ignite Manager plugin should be enabled and configured. The plugin allows for role based monitoring of critical server infrastructure and includes automation for restarting services based on the role detected on the device. The individual management packs should be configured to only look at devices under service plans.
Note on A68: Best Practice: The Virtualization Manager should be installed and enabled. Credentials should be configured for all clients with ESXi hosts. Passwords should ideally be unique for each client.

## User Accounts Review
User Accounts Review
Back to Audit Phase
User Review
Default User Settings |  |  | Default User Settings Review Action Items
Review Item | Value |  | Task | Approved | Completed
Account Lockouts Property Enabled
Users Can Save Password
User Accounts | [6 empty] | User Review Action Items
Username | UserClasses | Audit Level | Last Logon | Integrator | SSO | Task | Approved | Completed
Review dormant CWA accounts.
[6 empty] | Review Super Admins. |  |  | LDAP Review
[6 empty] | Review users missing Audit Level Everything. |  |  | SSO Review
[6 empty] | Review users that haven't logged on in > 90 days. |  |  | User Metrics
[6 empty] | Review Integrator users. |  |  | Review User Audit Levels
[6 empty] | Review any users with "Test" in their name. |  |  | MFA/2FA Audit
[6 empty] | Review accounts missing SSO. |  |  | User Password Settings
System Lockouts
Back to Audit Phase
Note on A4: Best Practice: There are several best practice user settings to consider. LDAP - This can be setup, however with many partners moving to Azure AD, this can be troublesome. If Azure AD is available, ProVal recommends setting up SSO with Azure linked. Single Sign On - As ConnectWise pushes more of Automate to the cloud we will see less and less authentication via the CWA Database. SSO is the best way to prep for the future of the product. Lockouts - Ensuring that account lockouts are happening on failed logins helps increase security. ProVal recommends enabling the account lockout feature if it's not already enabled. Save Password - Typically in the thick client users are allowed to "save" their password for their login. We discourage this as a safety concern. Even with mandatory Multifactor Authentication it is best practice to not allow users to store passwords. Audit Level - ProVal recommends that all users have the audit level of "Everything." Firstly this helps keep tabs on what changes are made in Automate and it makes it easier to keep an eye on the system. The other advantage is several actions are able to be undone, so keeping track of those items might help fix something done accidentally.
Note on A9: Best Practice: Stale user accounts should be removed. Appropriate user classes should be assigned based on the users’ role within the company. All users should be set to the audit level “Everything”. ProVal recommends that users should not be allowed to save their passwords in the control center login screen. Account lockouts should be enabled after 5 failed login attempts. LDAP or SSO can be enabled to help simply user management.

## Patch Review
Patch Manager Review
Back to Audit Phase
Patch Manager Audit
GroupName | MachinesinGroup | UpdatePolicy | PolicyStyle | StartTime | Duration | RebootPolicy | ApprovalPolicies | Notes
Back to Audit Phase
Note on A4: Best Practice – Installing patches: Workstations should patch daily with an afternoon window being best. If patching is done overnight, daytime patching should be enabled. When agents miss their window they are then patched the next time they are online. Servers should patch weekly. Best Practice – Rebooting machines that require a reboot: Workstations should use the Suppress and Reboot option. This allows workstations to reboot when most convenient for the user. Reboots can be set with a deadline to ensure compliance. ProVal recommends a pop-up reminder every 120 minutes, and a deadline/forced reboot after 72 hours, with a 15 minute deadline message. Servers should use the “During +30 minute” reboot policy or scheduled reboot windows for an appropriate reboot time. Host Servers should be patched on a different day than any other role based server but can follow the above best practice. Host servers should have "pausing" enabled on Host shutdown. Please notify the primary consultant if there are any exceptions or clarifications required for any clients.

## Antivirus Review
Antivirus Review
Back to Audit Phase
Antivirus Review |  |  | Antivirus Review Action Items
Review Item | Value |  | Task | Approved | Completed
Managed Solution
Defender Priority Needs Adjusting?
Plugin installed/configured?
Antivirus Data
AV Detection Data
Count Machines | AV Name | VScanID
Note on A3: Best Practice: If available, the vendors plugin should be installed and enabled. These plugins typically provide installation scripts or built-in functionality to easily and efficiently deploy the antivirus application.
Note on A9: Best Practice: If available, the vendors plugin should be installed and enabled. These plugins typically provide installation scripts or built-in functionality to easily and efficiently deploy the antivirus application.

## CW Control Review
ConnectWise Control Review
Back to Audit Phase
CWC Review |  |  |  | Control Review Action Items
Review Item | Value |  |  | Task | Approved | Completed
Control Patch Version
SSL Configuration
Multi-Factor / Two Factor Authentication Users |  |  |  | Control MFA Review Action Items
Review Item | Value |  |  | Task | Approved | Completed
Number of Users Without 2FA |  |  |  | Review users/admins missing 2FA.
Number of Admins Without 2FA
Extensions Review | [5 empty] | Extensions Review Action Items
Extension Name | Installed | Configured | Up To Date | Completed |  | Task | Approved | Completed
Advanced Configuration Editor
ConnectWise Automate Integration
RMM+
ConnectWise Manage Integration
Back to Audit Phase
Note on A3: Best Practices: CW Control Patch: Keeping Automate fully patched is essential to have a stable system. It ensures bugs are fixed and provides new features. SSL Config: Enabling SSL on the Control server ensures that connections to the Web Portal are encrypted and secure.
Note on A8: Best Practice: All users that have access to CW Control should have MFA/2FA, including the Admin user. This helps prevent unauthorized access to the application and, by extension, end user machines.
Note on A22: Best Practice: The App.config & Web.config extensions should be installed, as they allow for customization of ConnectWise Control. Everything else is optional, but useful and ProVal recommends installing and using the above extensions
Note on A27: Optional

## Audit Phase Action Items
Audit Phase Action Items - Consolidated
Back to Audit Phase | Back to TOC
Action Items
Task | Approved | Completed | FromTable
P1_HardwareActions
P1_HardwareActions
P1_PortsActions
P1_Myiniactions
P1_Myiniactions
P1_dbtablesactions
P1_BrandingAction
P1_CCbrandingAcion
P1_SSLAction
P1_AccessModesAction
P1_ScriptReviewActions
P1_ScriptEngineActions
Load in ProVal best practice Schedules |  |  | P1_SchedulesAction
P1_EmailAction
P1_PluginReviewActions
P1_ADpluginAction
P1_ReportCenAction
P1_ReportCenAction
P1_IgniteManagerAction
P1_VirtManagerAction
P1_UserReviewAction
P1_DefaultUserAction
P1_PatchManReviewAction
Implement monitor solution? |  |  | P1_PatchWin10Action
Script Imported and setup? |  |  | P1_PatchWin10Action

## Impact Phase
Impact Phase Review
Back to TOC
In the Impact Phase of the onboarding, ProVal will review the following items in your system:
Ignite Review
Location Level Ignite Review
Default Extra Data Field Review
Environment Cleanup
Agents Not Checking In
Missing Drives Review
Missing Roles
Groups Review
PSA & Ticket Review
Ticket Volume Review
Ticket Noise Review
Tickets in Database
Manage Plugin: Comment Placement
Manage Plugin: Auto-Import Review
Manage Plugin: Service Boards Review
Manage Plugin: Asset Sync Review
Manage Plugin: Category Mapping Discussion
Impact Phase Action Items
Consolidated List

## Ignite Review
Ignite Review
Back to Impact Phase
Default EDF Settings |  | Default EDF Action Items
Review Item | Setting | Task | Approved | Completed
Server Service Plan
Workstation Service Plan
Enable Onboarding
Server Patching
Workstation Patching
Note on A4: Best Practice: The Location Level Default Extra Data Fields should be setup with the system defaults for new clients/locations and the boxes should be changed to manage by exception.
Note on A12: Best Practice: All sites should be configured with a service plan, even if that service plan indicates that no services are applied. (NonContract service plan.) This helps verify which clients are managed or not managed based on their service plans. The below data indicates sites that may be out of compliance or may need additional configuration.

## Environment Cleanup
Environment Cleanup
Back to Impact Phase
Environment Review
Out of Date Data |  |  | Out of Date Data Action Items
Review Item | Value |  | Task | Approved | Completed
ProVal Maintenance Script Running?
Total Missing Drives
Total Not Currently Detected Roles
Groups Review
GroupID | GroupPath | GroupName | # Machines | Template Name | AutoJoinScript | AutoJoin Name | Internal | Remote | Total | Scripts | Master | Group Notes | Recommendation | ProVal Notes
Groups Review Action Items
Task | Approved | Completed
Back to Impact Phase
Note on A5: Best Practice: Missing Drives Missing drives should be removed, otherwise false alerts can be generated and waste valuable technician time. The Remove Nonexistent Drives script can be scheduled to run against the Automate server to automate the removal process on a scheduled basis. Not Detected Roles Not currently detected roles should be removed, otherwise role based monitoring will generate false alerts. The Remove Not Detected Roles script can be scheduled to run against the Automate server to automate the removal process on a scheduled basis.
Note on A11: Best Practice: Groups are a great way to create functional or organizational units in Automate. However, groups can lose their purpose over time, or can be better serviced via internal monitor. We will review and discuss all non-standard groups in the environment and decide whether it is best to keep/delete/modify/replace groups in the environment to make things more efficient or easy to manage. Action items are below the table.

## PSA & Ticket Review
PSA & Ticket Review
Back to Impact Phase
PSA Plugin Integration and Configuration
Default Service Boards |  | Default Service Board Action Items
Ticket Type | Service Board | Task | Approved | Complete
Control Center Tickets
Automate Tray Tickets
Monitor/Script/Email Tickets
Service Board Audit |  | Service Board Action Items
Review Item | Value | Task | Approved | Complete
Service Board Mapping | X of X | Review boards that are not imported.
Service Board Name | Imported?
Manage <--> Automate Mappings |  | CWA / CWM Mapping Action Items
Review Item | Value | Task | Approved | Complete
Ticket Status Mapping
Ticket Priority Mapping
Total Category Mapping
Back to Impact Phase
Note on A5: Best Practice: All the default service boards should be set. Default service boards should only be used as a fallback, with ticket mapping directing tickets to the appropriate boards.
Note on A11: Best Practice: All service boards that Automate tickets will be synced with, or moved to, must be synced with the Manage plugin in Automate. If an Automate ticket is moved to a board that is not synced with the Automate plugin, the sync between Automate and Manage will be broken.
Note on A27: Best Practice: Map all statuses, all priorities, and all ticket categories to ensure tickets flow to the correct boards in the PSA. Unmapped statuses and priorities will cause ticket sync failures. All values should be mapped between Automate and the PSA. Unmapped tickets will be directed to the default boards configured.

## Impact Phase Action Items
Impact Phase Action Items - Consolidated
Back to Impact Phase |  | Back to TOC
Action Items
Task | Approved | Completed | FromTable
P2_IgniteReviewAction
P2_IgniteReviewAction
P2_IgniteReviewAction
P2_DefaultEDFAction
P2_DefaultEDFAction
P2_DefaultEDFAction
P2_NoCheckinActions
P2_NoCheckinActions
P2_OutOfDateActions
P2_OutOfDateActions
P2_GroupReviewActions
P2_GroupReviewActions
P2_GroupReviewActions
P2_GroupReviewActions
P2_TicketVolAction
P2_TicketNoiseAction
P2_DefServiceBoardAction
P2_ServiceBoardAction
P2_MappingsAction
P2_TicketCatAction
Test | Yes |  | P2_CWMPluginOptionalAction

## Automation Phase
Automation Phase Review
Back to TOC
In the Automation Phase of the onboarding ProVal will review the following items in your system:
Monitoring Audit
ProVal Best Practice Monitoring
Monitor Audit
Broken Monitor Audit
Offline Server Monitoring
Ignite Manager Configuration
Virtualization Manager Monitoring
Network Device Review
Probe Review
Network Device Monitoring
Automation Phase Action items
Consolidated List

## Monitor Audit
Monitor Audit | Legend
Back to Automation Phase | Good | Replace
Monitor Audit | Disable | Question
Note on D2: This is a monitor we would like to keep in production.
Note on E2: These are monitors ProVal would like to replace with custom versions.
Note on A3: This list will display every group based or global monitor in the environment and any pertinent information about the monitors. Please review all monitors and decide on which monitors to keep, which monitors to replace, and which monitors to remove.
Note on D3: This is a monitor we would want to remove from production or possibly even remove from the environment
Note on E3: These are monitors that we were not sure what the original purpose might have been. We would like to discuss this monitor and see what we can do to improve it.

## Best Practice Monitoring
ProVal Best Practice Monitors
Back to Automation Phase
Best Practice Monitors
Any items highlighted yellow are optional/may not apply to all MSPs
Monitor Name | Recommended Alert Template | Imported? | Enabled? | Up-to-Date? | Notes
ProVal - CWA Server Monitoring Solution Set
ProVal - Production - Active Directory - Account Disabled [G] | Default - Create Automate Ticket
ProVal - Production - Active Directory - ADPluginUser - Create/Update | ~Autofix - Create AD Plugin Service Account
ProVal - Production - Active Directory - Domain Admin Recently Created | △ Custom - Ticket Creation - Computer
ProVal - Production - Active Directory - Enabled Test Accounts | △ Custom - Ticket Creation - Computer
ProVal - Production - Active Directory - GPO Modified | Default - Create Automate Ticket
ProVal - Production - Active Directory - Password Expires This Week [G] | ~Autofix - Notify User of Password Expiration
ProVal - Production - Active Directory - Sync Out of Date | ~Autofix Action - Active Directory Sync Out of Date [RMM+]
ProVal - Production - Agent - Crystal Disk Info Audit | △ Custom - Ticket Creation - Computer
ProVal - Production - Agent - CW Control Needs Repair | ~Autofix Action - Repair CW Control
ProVal - Production - Agent - Dell Hardware Monitoring | △ Custom - Ticket Creation - Computer
ProVal - Production - Agent - Drive - Space Critical | Default - Create Automate Ticket
ProVal - Production - Agent - Drive Errors and Raid Failures | △ Custom - Ticket Creation - Computer
ProVal - Production - Agent - Drive Space Check - Modified | △ Custom - Autofix - ProVal Drive Space Cleanup - Modified
ProVal - Production - Agent - Duplicate Serial Number
ProVal - Production - Agent - HP Hardware Monitoring | △ Custom - Ticket Creation - Computer
ProVal - Production - Agent - No Checkin for More Than 30 Days* | △ Custom - Autofix - Offline Agent Remediation (RMM+)
ProVal - Production - Agent - Offline Server | ~Autofix Action - Server Offline (Excluding VMs) - RMM+
ProVal - Production - Agent - Shutdown Unexpected | △ Custom - Ticket Creation - Computer
ProVal - Production - Automate - Less Than X Licenses Remaining [G] | Default - Create Automate Ticket
ProVal - Production - Automate - Machines With Stuck Commands [G] | ~Autofix Action - Clear Stuck Commands
ProVal - Production - Automate - Ticket Sync Unsuccessful | ~DEV - Autofix - Ticket Sync Failed
ProVal - Production - Automate - Unsynced Ticket Comment | ~Custom Email RAWSQL Monitor set results to the Partner
ProVal - Production - Certificate Expiration < 30 Days | △ Custom - Ticket Creation - Computer
ProVal - Production - Crystal Disk Audit (Script) | △ Custom - Autofix - Initiate Crystal Disk Audit Script
ProVal - Production - Ethernet Speed Less Than 100Mbps | △ Custom - Ticket Creation - Computer
ProVal - Production - Hyper-V - Integration Service Out of Date | Default - Create Automate Ticket
ProVal - Production - Hyper-V - Replication Status | Default - Create Automate Ticket
ProVal - Production - Machine Back Online | N/A
ProVal - Production - Patching - Automate Patch Scans - Repair | ~Autofix - Repair Failing Patch Scans
ProVal - Production - Patching - Empty Patch Window | ~Empty Patch Window Autofix
ProVal - Production - Patching - Windows 10 Build Upgrades [G] | △ Custom - Autofix - Start Windows 10 Build upgrade
ProVal - Production - Security - Possible Brute Force Attack [G] | △ Custom - Ticket Creation - Computer
ProVal - Production - Security - Stale Bitlocker Data [G]
Proval - Production - Security event logs cleared/deleted | Default - Create Automate Ticket
ProVal - Production - Software - Missing Vendor Admin Software | △ Custom - Ticket Creation - Computer
ProVal - Production - Vendor Specific - HP iLO Health Report Check
ProVal - Production - Windows - Fast Boot Enabled [Role] | ~Autofix Action - Disable Fastboot
Script - Service - Restart | Alert Template
Update Orchestrator Solution | ~Autofix - Update Orchestrator Disable
Windows License Monitor | Default - Create Automate Ticket
ProVal - Production - ESXi Bad Sensor
ProVal - Production - ESXi Host Not Communicating > 3 Days
ProVal - Production - ESXi Old Snapshots Detected > 3 Days
ProVal - Production - ESXi Storage Space < 10%
Back to Automation Phase
Note on A3: This is the best practice list of monitors that ProVal recommends. Most monitors, if not all, should be used by MSPs to watch their devices and their Automate application. ProVal has a lot more available content than what is available on this list. Please ask your consultant for a full list of all available content or refer to the ProSync plugin.
Note on A11: Discuss GPO auditing solution and monitoring
Note on B12: Options: Run autofix that emails the user directly, please supply desired language in the script. This can just generate a ticket into manage and then setup a workflow that has the matching contact to notify them from Manage.
Note on A15: Windows Only
Note on A20: Discuss best practice automation for clearing duplicate serial numbers.

## Broken Monitors
Broken Monitors
Back to Automation Phase
Broken Monitors Review |  |  |  | Broken Monitors Action Items
Monitor Name | DataOut | Group Notes | Group Applied | Task | Approved | Complete
Back to Automation Phase
Note on A3: Sometimes monitors to not write the correct values back into the database which can cause alerts to be missed. This is not something that happens very often, but it does happen from time to time. ProVal will review any of these monitors with potential issues and get the repaired. This is an item we will review monthly as part of keeping the system healthy.

## Offline Server Monitoring
Offline Server Monitoring
Back to Automation Phase
Offline Server Audit |  | Offline Server Action Items
Audit Item | Value | Task | Approved | Completed
Heartbeat Enabled?
Monitor has alerts in the history table and is creating tickets?
Using RMM+?
Back to Automation Phase
Note on A3: Best Practice: As one of the most critical monitors in Automate, it is imperative that this monitor is functioning properly. The default LT – Offline Servers monitor works, however it does not account for some heartbeat scenarios that may cause the monitor to not trigger properly. ProVal recommends installing out best practice version of this monitor that handles for broken heartbeat scenarios. Ideally, the monitor should be configured with the ~Autofix Action Server Offline Script alert template which then calls the Server Offline alert template. This configuration runs the script to perform basic troubleshooting, which is appended to the ticket. ProVal also finds that the default thresholds lead to some false positives. We encourage partners to adjust the timing from the standard 6 minute no check-in and 30 second no heartbeat to between 8-12 minutes for last contact and 2-4 minutes no heartbeat.

## Ignite Manager Monitoring
Ignite Manager Monitoring
Back to Automation Phase
Ignite Manager Plugins
Ignite Manager Monitors | [5 empty] | Ignite Manager Monitoring Action Items
Management Pack | Monitor | Alert Template | Ticket Category | Data Collection | Applies to Role | Task | Approved | Completed
Back to Automation Phase
Note on A3: Best Practice: All Ignite Manager management packs should be updated, installed, and enabled. These management packs provide current monitoring for all types of servers and applications. Our standard monitoring setup only alerts on critical services/events and does not alert on most performance metrics. Please review the list of monitors below by server role and our best practice for each management pack.

## Virt Manager Monitoring
Virtualization Manager Monitoring
Back to Automation Phase
Virtualization Manager Monitors
Virtualization Manager Monitor Action Items
Applies To | Monitor | Enabled | Operator | Value | Interval | Alert Template | Task | Approved | Completed
Back to Automation Phase
Note on A3: Best Practice: As mentioned earlier during the onboarding, the Virtualization Manager can help manage and monitor your ESXi and Hyper-V hosts as well as their guests/virtual machines. Part of this implementation is going through available monitors and the ProVal best practice monitors. ProVal has custom alerting for the Virtualization Manager that makes the tickets significantly more useful than the stock monitors.
Note on F5: In minutes

## Probe Review
Network Device Monitoring
Back to Automation Phase
Probe Review
Network Probe Action Items
Client | Location | Probe Status | Possible Probe | Probe Version | Notes | Task | Approved | Complete
Back to Automation Phase
Note on A3: Best Practice: The probe may not be the perfect solution for network monitoring but it is at least a good jumping off point for basic monitoring and gathering some SNMP information. The probe can be used to do things like backup device configurations, provide up/down monitoring for network devices, deploy agents, and other various tasks. ProVal suggests having a probe at each site, ideally on a machine that is online 24x7 and that has good access to the end client network. A Domain Controller is a good choice for the network probe. All network probes should be running that latest version of the probe and we suggest ensuring all probes are running V2.

## Network Device Monitoring
Network Device Monitoring
Back to Automation Phase
Network Device Monitoring
Network Device Monitoring Action Items
Client | Location | Network Device | Set to Alert | Alert Template | Notes | Task | Approved | Completed
Back to Automation Phase
Note on A3: Best Practice: The Network device management screen allows users to setup basic online/offline monitoring for network devices. Below is an audit for any devices with this setup or not setup. The probe is not the most reliable method for this when there are other great tools like Auvik, PRTG, or Logic Monitor. But the probe can get the ball rolling on monitoring for the network devices at a base level.

## Automation Phase Action Items
Automation Phase Action Items - Consolidated
Back to Automation Phase |  | Back to TOC
Action Items
Task | Approved | Completed | FromTable
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_ProValBestPractMonitors
W3_OfflineServerAction
W3_IgniteManPluginAction
W3_IgniteManPluginAction
W3_IgniteManMonitorsAction
W3_IgniteManMonitorsAction
W3_VirtManMonAction
W3_NetProbeAction
W3_NetProbeAction
W3_NetProbeAction
W3_NetDeviceMonAction
W3_NetDeviceMonAction

## Client Success Phase
Client Success Phase Review
Back to TOC
In the Client Success Phase of the onboarding ProVal will work on wrapping up the project!
Action Items
Consolidated Action Item Review
Schedule Meetings
Training Call
Monthly Admin Call
Wrap up Call & Project Completion
Approval
Notes

## Consolidated Action Items
Consolidated Action Items
Back to Client Success Phase |  | Back to TOC
Action Items
Task | Approved | Completed | FromTable
P1_HardwareActions
P1_HardwareActions
P1_PortsActions
P1_Myiniactions
P1_Myiniactions
P1_dbtablesactions
P1_BrandingAction
P1_CCbrandingAcion
P1_SSLAction
P1_AccessModesAction
P1_ScriptReviewActions
P1_ScriptEngineActions
Load in ProVal best practice Schedules |  |  | P1_SchedulesAction
P1_EmailAction
P1_PluginReviewActions
P1_ADpluginAction
P1_ReportCenAction
P1_ReportCenAction
P1_IgniteManagerAction
P1_VirtManagerAction
P1_UserReviewAction
P1_DefaultUserAction
P1_PatchManReviewAction
Implement monitor solution? |  |  | P1_PatchWin10Action
Script Imported and setup? |  |  | P1_PatchWin10Action
P1_AVAction
P1_CWCAction
P1_CWCMFAAction
P1_CWAExtensionAction
P2_IgniteReviewAction
P2_IgniteReviewAction
P2_IgniteReviewAction
P2_DefaultEDFAction
P2_DefaultEDFAction
P2_DefaultEDFAction
P2_NoCheckinActions
P2_NoCheckinActions
P2_OutOfDateActions
P2_OutOfDateActions
P2_GroupReviewActions
P2_GroupReviewActions
P2_GroupReviewActions
P2_GroupReviewActions
P2_TicketVolAction
P2_TicketNoiseAction
P2_DefServiceBoardAction
P2_ServiceBoardAction
P2_MappingsAction
P2_TicketCatAction
P2_CWMPluginOptionalAction
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_ProValBestPractMonitors
P3_OfflineServerAction
P3_IgniteManPluginAction
P3_IgniteManPluginAction
P3_IgniteManMonitorsAction
P3_IgniteManMonitorsAction
P3_VirtManMonAction
P3_NetProbeAction
P3_NetProbeAction
P3_NetProbeAction
P3_NetDeviceMonAction
P3_NetDeviceMonAction

## Schedule Meetings
Schedule Meetings
Back to Client Success Phase
Call Schedules
Task | Date Scheduled | Time Scheduled | Approved | Complete
Team training
Monthly Call
Back to Client Success Phase
Note on A3: Training: ProVal provides a training for level 1-3 help desk team members aimed at teaching the team how to use Automate more effectively. The main mission of this training is to help the team understand all of the functions of the RMM so they can work without interrupting end users. This training should better enable them to support from the backend using Automate. This training will be recorded and shared back to the MSP. Monthly Call: During this call, ProVal will sit down with the MSP for about an hour and discuss the state of the environment, any issues or overarching goals the MSP is trying to accomplish, as well as any new content developed by ProVal that may help the MSP. This is the ideal forum to bring up any new development items the MSP may be interested in pursuing.

## Wrap Up Call-Project Completion
Project Completion
Back to Client Success Phase |  | Back to TOC
Wrap up call
Task | Approved | Completed | Date | Consultant Initials
Wrap up Call
Project Complete
Notes
Task | Approved | Completed
Back to Client Success Phase
Note on A3: Completing the project: Please ensure that all action items are completed, or that any remaining items are converted to tickets. Please receive a verbal confirmation that the MSP feels the project is complete and then close out the project.
Note on A10: Notes: Please write up any items that didn't fit into the original SOW or that we are covering outside of the standard SOW for the MSP.

## Data Sources
Patching Validation | Reboot Validation | Reboot Mode
Do Nothing | Suppress Reboot and Alert | Not Set
Enable Windows Update Default | During Windows Update | Now
Disable Windows Update | Scheduled | Ask
Disable Windows Update - UI Disabled | Disable Reboot Window - Follow Mode Setting | Ask then Allow
Managed Mode |  | Ask then Deny
Managed Mode - UI Disabled |  | N/A