## PVL-EUR-ESX-01 Prod
Plan 1: Movement of VMs one by one and changeing ip as per current setup for the vm which has been moved, abd changing the record if any as per below on cloudflare and WAN ip
Plan 2: Change of LAN and VPN IP address and configuration
1 | Esxi-01 |  | Confirmation needed from application owner
Scenario 1. If we have enough resources after removing unwanted vm then we can use this esxi, which is not likely the case
Scenario 2. If we don’t have enough resources after removing unwanted vm then we have to purcahsed new server.Or decrease the resources of current vm
| Rename Host name to | PVL-EUR-ESX-01
2 | Pfsense |  | Internal IT
Remain in same esxi
| LAN IP will be changed to | 10.0.2.1
Changes need to be done on firewall
- Take backup of the pfsense vm and config
- Enable temporary WAN access during moving VM's and during changes done in FW
| In Ipsec vpn (prod1 to VDI)need to change remote subnet ip to | 10.0.1.0/24
| Need to create Ipsec VPN Tunnel (prod1 to Dev) Remote Subnet need to change to IP | 10.0.3.0/24
| Need to create Ipsec VPN Tunnel (prod1 to USA HQ) Remote Subnet need to change to IP | 10.0.4.0/24
| Open VPN Tunnel for end user the IP range | 10.0.2.240 to 10.0.2.250
| Rename Host name to | PVL-EUR-FW-01
3 | Connectwise |  | Chase
Remain in same esxi
| LAN IP will be changed to | 10.0.2.10
| On Pfsense NAT ip for HTTPS need to be changed to | 10.0.2.10
| Rename Host name to | PVL-EUR-CWM-01 | Renaming might cause issues to the service, need confimation from application owner
4 | EUR-GER-DB01 |  | Mohit/David
Remain in same esxi
| LAN IP will be changed to | 10.0.2.12
On Pfsense no NAT or firewall rule for this server
| Rename Host name to | PVL-EUR-DB-01 | Renaming might cause issues to the service, need confimation from application owner
5 | EUR-GER-VAC01 |  | Puneet
Remain in same esxi
| LAN IP will be changed to | 10.0.2.14
| On Pfsense NAT ip for port 1280 need to be changed to | 10.0.2.14
| On Pfsense NAT ip for port 6180 need to be changed to | 10.0.2.14
| Need WAN Virtual IP | We can use lamp
| DNS record need to be change @ cloud flare | IP Needed
| Rename Host name to | PVL-EUR-VAC-01 | Renaming might cause issues to the service, need confimation from application owner
6 | Kaseya |  | Mohit/David
Remain in same esxi
| LAN IP will be changed to | 10.0.2.16
| On Pfsense NAT ip for port 80 need to be changed to | 10.0.2.14
| On Pfsense NAT ip for port 443 need to be changed to | 10.0.2.14
| On Pfsense NAT ip for port 5721 need to be changed to | 10.0.2.14
| Rename Host name to | PVL-EUR-VSA-01 | Renaming might cause issues to the service, need confimation from application owner
7 | LAMP | 10.0.2.34 | David/Mohit/Sebastian
| LAN IP will be changed to | 10.0.2.34
| On Pfsense NAT ip for port 1433 need to be changed to | 10.0.2.34
| On Pfsense NAT ip for port 80 need to be changed to | 10.0.2.34
| On Pfsense NAT ip for port 443 need to be changed to | 10.0.2.34
| On Pfsense NAT ip for port 3306 need to be changed to | 10.0.2.34
| Rename Host name to | PVL-EUR-LMP-01 | Renaming might cause issues to the service, need confimation from application owner
8 | OS Tickets |  | Internal IT/Sebastian/Mohit
Remain in same esxi
| LAN IP will be changed to | 10.0.2.32
| On Pfsense NAT ip for port 80 need to be changed to | 10.0.2.32
| On Pfsense NAT ip for port 443 need to be changed to | 10.0.2.32
| On Pfsense NAT ip for port 21 need to be changed to | 10.0.2.32
| On Pfsense NAT ip for port 3306 need to be changed to | 10.0.2.32
| On Pfsense NAT ip for port 8087 need to be changed to | 10.0.2.32
| On Pfsense NAT ip for port 8080 need to be changed to | 10.0.2.32
| Rename Host name to | PVL-EUR-OST-01 | Renaming might cause issues to the service, need confimation from application owner
9 | AuthAnvil |  | Internal IT
Scenario 1. If we have enough resources after removing unwanted vm then we have to move this vm from esxi-02 by migration option in vm
Scenario 2. If we don’t have enough resources after removing unwanted vm then we have to purchase new server and install esxi and move the VM from esxi-02 to new esxi.
| LAN IP will be changed to | 10.0.2.22
| On Pfsense no NAT or firewall rule for this server | None
| Rename Host name to | PVL-EUR-ATV-01
10 | CW_Automate |  | Chase/Stephen
Scenario 1. If we have enough resources after removing unwanted vm then we have to move this vm from esxi-02 by migration option in vm
Scenario 2. If we don’t have enough resources after removing unwanted vm then we have to purchase new server and install esxi and move the VM from esxi-02 to new esxi.
| LAN IP will be changed to | 10.0.2.24
| On Pfsense NAT ip for port 8040-8041 need to be changed to | 10.0.2.24
| On Pfsense NAT ip for port 80 need to be changed to | 10.0.2.24
| On Pfsense NAT ip for port 443 need to be changed to | 10.0.2.24
| On Pfsense NAT ip for port 75 need to be changed to | 10.0.2.24
| On Pfsense NAT ip for port 3306 need to be changed to | 10.0.2.24
| On Pfsense NAT ip for port 70-75 need to be changed to | 10.0.2.24
| On Pfsense NAT ip for port 40000-40050 need to be changed to | 10.0.2.24
| On Pfsense NAT ip for port 80 need to be changed to | 10.0.2.24
| Need WAN Virtual IP | We can use OST IP
| DNS record need to be change @ cloud flare | IP Needed
| Rename Host name to | PVL-EUR-CW-01 | Renaming might cause issues to the service, need confimation from application owner
11 | Shadow Control |  | Puneet
Scenario 1. If we have enough resources after removing unwanted vm then we have to move this vm from esxi-02 by migration option in vm
Scenario 2. If we don’t have enough resources after removing unwanted vm then we have to purchase new server and install esxi and move the VM from esxi-02 to new esxi.
| LAN IP will be changed to | 10.0.2.26
| On Pfsense NAT ip for port 8443 need to be changed to | 10.0.2.26
| On Pfsense NAT ip for port 25 need to be changed to | 10.0.2.26
| On Pfsense NAT ip for port 587 need to be changed to | 10.0.2.26
| On Pfsense NAT ip for port 5556 need to be changed to | 10.0.2.26
| On Pfsense NAT ip for port 22 need to be changed to | 10.0.2.26
| On Pfsense NAT ip for port 443 need to be changed to | 10.0.2.26
| On Pfsense NAT ip for port 80 need to be changed to | 10.0.2.26
| Need WAN Virtual IP | 46.4.162.35
| DNS record need to be change @ cloud flare | IP Needed
| Rename Host name to | PVL-EUR-SC-01 | Renaming might cause issues to the service, need confimation from application owner
12 | LAMPDB |  | Mohit/david
| LAN IP will be changed to | 10.0.2.36
NO NAT Rule ON pfsense for this server
| Rename Host name to | PVL-EUR-LMDB-01 | Renaming might cause issues to the service, need confimation from application owner
13 | PVL-EUR-File-01 |  | Stephen and Dave
Nee to moved from HPV-01
Scenario 1. If we have enough storage after removing unwanted vm then we have to move this vm from HPV-01 to esxi-01 by migration option in vm
Scenario 2. If we don’t have enough resources after removing unwanted vm then we have to purchase new server and install esxi and move the VM from HPV-01 hyperv to new esxi.
| LAN IP will be changed to | 10.0.2.30
| On Pfsense NAT ip for port 443 need to be changed to | 10.0.2.30
| On Pfsense NAT ip for port 5721 need to be changed to | 10.0.2.30
| On Pfsense NAT ip for port 8040 need to be changed to | 10.0.2.30
| On Pfsense NAT ip for port 8441 need to be changed to | 10.0.2.30
| DNS record need to be change @ cloud flare | IP Needed
| Need WAN Virtual IP | IP Needed
| WAP IP Range | 10.0.2.65-10.0.2.80
| Switches IP Range | 10.0.2.45-10.0.2.60
| Printer IP Range | 10.0.2.85-10.0.2.95
| NAS SAN IP Range | 10.0.2.100-10.0.2.110
| IP Phone IP Range | 10.1.2.10-10.1.2.100
| DHCP Scope | 10.0.2.125-10.0.2.225
| Open VPN Tunnel for end user the IP range | 10.0.2.240-10.0.2.250
| US VPN DHCP Scope | 10.2.2.0/24
DNS: Open DNS Cisco umbrella
| DNS1: | 208.67.222.222
| DNS2: | 208.67.220.220

## PVL-EUR-ESX-02 Dev
Plan 1: Movement of VMs one by one and changeing ip as per current setup for the vm which has been moved, and changing the record if any as per below on cloudflare and WAN ip
Plan 2: Change of LAN and VPN IP address and configuration
1 | ESXi-02 | IP | Confirmation needed from application owner
| Scenario 1. If we have enough resources after removing unwanted vm then we can use this esxi, which is not likely the case |  | Internal IT
Scenario 2. If we don’t have enough resources after removing unwanted vm then we have to purcahsed new server.Or decrease the resources of current vm
| LAN IP | None
| Rename Host name to | PVL-EUR-ESX-02
2 | Pfsense |  | Internal IT
| New LAN IP | 10.0.3.1
| Creating Ipsec VPN tunnel (Dev to Prod1) IP of remote subnet need to change | 10.0.3.0/24
| Creating Ipsec VPN tunnel (Dev to USA HQ) IP of remote subnet need to change | 10.0.4.0/24
| Open VPN Tunnel for end user the IP range | 10.0.3.240 to 10.0.3.250
| Rename Host name to | PVL-EUR-FW-02
3 | CW-Automate |  | Chase/Stephen
VM Need to be build
| New LAN IP | 10.0.3.10
| New NAT rules to be created as per requirement | 10.0.3.10
| Need WAN Virtual IP | IP Needed
| DNS record need to be change @ cloud flare | IP Needed
| Rename Host name to | PVL-EUR-CWA-02
4 | Conenctwise |  | Chase
VM Need to be build
| New LAN IP | 10.0.3.12
| New NAT rules to be created as per requirement | 10.0.3.12
| Need WAN Virtual IP | IP Needed
| DNS record need to be change @ cloud flare | IP Needed
| Rename Host name to | PVL-EUR-CWM-02
5 | Kaseya |  | Mohit/David
VM Need to be build
| New LAN IP | 10.0.3.14
| New NAT rules to be created as per requirement | 10.0.3.14
| Need WAN Virtual IP | IP Needed
| DNS record need to be change @ cloud flare | IP Needed
| Rename Host name to | PVL-EUR-VSA-02
6 | ORL-RDS1 |  | Internal IT
Scenario 1. If we have enough resource after removing unwanted vm then we have to move this vm from from Orlando Hyperv to esxi2
Scenario 2. If we don’t have enough resources after removing unwanted vm then we have to purchase new server and install esxi and move the VM from Orlando hyperv to new esxi.
| New LAN IP | 10.0.3.30
| On Pfsense test NAT ip for port 80 need to be changed to | 10.0.3.30
| On Pfsense test NAT ip for port 443 need to be changed to | 10.0.3.30
| Rename Host name to | PVL-EUR-RDS-02
7 | Test Machines |  | Internal IT and Automation team
Need to be moved from Orlando Hyperv to PVL-EUR-HPV-01 and renamed to below
Win Server 2012 Dev
Win Server 2016 Dev
Win Server 2019 Dev need to be build
Win 7 Dev
Win 10 Dev 1709
Win 10 Dev 1803
Win 10 Dev 1903
No NAT Rules on pfsense for the test machines
| WAP IP Range | 10.0.3.65-10.0.3.80
| Switches IP Range | 10.0.3.45-10.0.3.60
| Printer IP Range | 10.0.3.85-10.0.3.95
| NAS SAN IP Range | 10.0.3.100-10.0.3.110
| IP Phone IP Range | 10.1.3.10-10.1.3.100
| DHCP Scope | 10.0.3.125-10.0.3.225
| Open VPN Tunnel for end user the IP range | 10.0.3.240-10.0.3.250
| US VPN DHCP Scope | 10.2.2.0/24
DNS: Open DNS Cisco umbrella
| DNS1: | 208.67.222.222
| DNS2: | 208.67.220.220

## PVL-EUR-HPV-01 Internal
Plan 1: Movement of VMs one by one and changeing ip as per current setup for the vm which has been moved, abd changing the record if any as per below on cloudflare and WAN IP
Plan 2: Change of LAN and VPN IP address and configuration
1 | PVL-EUR-HPV-01 | LAN IP | Confirmation needed from application owner
| New LAN IP Need to be changed | 10.0.1.10 | Internal IT
2 | PVL-EUR-FW-03 Pfsense |  | Internal IT
| New LAN IP | 10.0.1.1
| In Ipsec vpn need to change remote netowrk(prod1-esxi-01) ip to | 10.0.2.1/24
| Open VPN Tunnel for end user the IP range | 10.0.1.240 to 10.0.1.250
3 | PVL-EUR-CB-01 |  | Internal IT
| New LAN IP | 10.0.1.12
4 | PVL-EUR-RDG-01 |  | Internal IT
| New LAN IP | 10.0.1.14
| On Pfsense NAT ip for port 443 need to be changed to | 10.0.1.14
5 | PVL-VDI-ATG-01 |  | Internal IT
| New LAN IP | 10.0.1.16
6 | PVL-VDI-Win10-Temp |  | Internal IT
| New LAN IP | 10.0.1.18
7 | EUR-GER-DC01 |  | Internal IT
We have to move this vm from esxi 1 to HPV-01
| New LAN IP | 10.0.1.20
| Need to rename host name to | PVL-EUR-DC-01 | Renaming a host name will impact the service its risky as it’s a domain controller
8 | EUR-GER-DC02 |  | Internal IT
VM Not needed
9 | RDS-01
| We have to move this vm from esxi-01 to HPV-01 |  | Internal IT
| New LAN IP | 10.0.1.22
| Need to rename host name to | PVL-EUR-RDS-01
10 | EUR-GER-VC01 |  | Internal IT
We have to move this vm from esxi-02 to HPV-01
| New LAN IP | 10.0.1.24
| Need to rename host name to | PVL-EUR-VC-01
| WAP IP Range | 10.0.1.65-10.1.4.80
| Switches IP Range | 10.0.1.45-10.0.1.60
| Printer IP Range | 10.0.1.85-10.0.1.95
| NAS SAN IP Range | 10.0.1.100-10.0.1.110
| IP Phone IP Range | 10.1.1.10-10.1.1.100
| DHCP Scope | 10.0.1.125-10.0.1.225
| Open VPN Tunnel for end user the IP range | 10.0.1.240-10.0.1.250
| US VPN DHCP Scope | 10.2.1.0/24
DNS: Open DNS Cisco umbrella
| DNS1: | 208.67.222.222
| DNS2: | 208.67.220.220

## HQ USA
Plan 1: Movement of VMs one by one and changeing ip as per current setup for the vm which has been moved, abd changing the record if any as per below on cloudflare and WAN ip
Plan 2: Change of LAN and VPN IP address and configuration
Pfsense
LAN IP will be changed to | 10.0.4.1
Changes need to be done on firewall
- Take backup of the pfsense vm and config
- Enable temporary WAN access during moving VM's and during changes done in FW
In open vpn tunnel(US HQ to Dev) ip need to be changed to | 10.0.4.240
Change of local IP of VPN Tunnel IP to DEV | 10.0.3.0/24
Open VPN Tunnel for end user the IP range | 10.0.4.240 to 10.0.4.250
Need to create Ipsec VPN Tunnel ( USA HQ-Prod1 ) Remote Subnet need to change to IP | 10.0.2.0/24
Need to create Ipsec VPN Tunnel ( USA HQ to DEV ) Remote Subnet need to change to IP | 10.0.3.0/24
Open VPN Tunnel for end user the IP range | 10.0.4.240 to 10.0.4.250
WAP IP Range | 10.0.4.65-10.0.4.80
Switches IP Range | 10.0.4.45-10.0.4.60
Printer IP Range | 10.0.4.85-10.0.4.95
NAS SAN IP Range | 10.0.4.100-10.0.4.110
IP Phone IP Range | 10.1.4.10-10.1.4.100
DHCP Scope | 10.0.4.125-10.0.4.225
Open VPN Tunnel for end user the IP range | 10.0.4.240-10.0.4.250
US VPN DHCP Scope | 10.2.1.0/24
DNS: Open DNS Cisco umbrella
DNS1: | 208.67.222.222
DNS2: | 208.67.220.220