## Project Planner
Kaseya Migration - Fresh Install
[6 empty] | Period Highlight: | 1 | Total Duration | Actual Start | % Complete | Actual (beyond plan) | % Complete (beyond plan)
ACTIVITY | OWNER | START WEEK | END WEEK | ACTUAL START | ACTUAL COMPLETION | PERCENT COMPLETE | PERIODS IN WEEKS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6
Requirements Mapping | ProVal & Meriplex | 1 | 1 | 0 | 0 | 0%
Requirements Review and Edits | ProVal & Meriplex | 1 | 1 | 0 | 0 | 0%
Installation Step by Step | ProVal | 1 | 2 | 0 | 0 | 0%
Post Installation Configuration | ProVal | 1 | 2 | 0 | 0 | 0%
Internal Testing | ProVal | 2 | 6 | 0 | 0 | 0%
Migration of Orgs & Agents | ProVal | 2 | 6 | 0 | 0 | 0%
Installation/Configuration - 3rd Party Modules | ProVal | 3 | 6 | 0 | 0 | 0%
Implementation - Policies & its Configuration | ProVal | 3 | 6 | 0 | 0 | 0%
Testing - Configuration | ProVal | 4 | 6 | 0 | 0 | 0%
Review Impact & Discussion - Custom | ProVal & Meriplex | 4 | 6 | 0 | 0 | 0%
Custom Configuration | ProVal | 4 | 6 | 0 | 0 | 0%
Final Review & Adjustments | ProVal | 5 | 6 | 0 | 0 | 0%
Inform Stakeholders of Change | ProVal & Meriplex | 6 | 6 | 0 | 0 | 0%
Review & Final Cutover | ProVal & Meriplex | 6 | 6 | 0 | 0 | 0%